## TODOS
TODOS:
- Show sidequests (Firn Air, Geophysics, Living Tent Setup, etc)
- Input column for actual hours and achieved depths

## Baseline 1 - Perfect, 24hr (hidden)
|  | Day | Drilling Critical Path | Working Day (hrs) | Drilling Day (hrs) | Cumulative Drilling Time (hrs) | Drilling Day (mins) | New Drilling Depth (m) | End of Day Drill Depth (m) | Drill Fluid Height (m) | Drill Fluid Used (Drums) | Bailing Day (hrs) | Cumulative Bailing Time (hrs) | Bailing Day (mins) | New Bailing Depth (m) | End of Day Bailing Depth (m) | Drill Fluid in Field (Drums) | Drill Fluid Planned Arrival (Drums) | Drill Fluid Still Required IN (Drums) | Ice Core Boxes Filled | Today's Ice Core Boxes Filled | Filled Ice Core Boxes in Field | Ice Core Boxes Planned Removal | Ice Core Box Flight Ready OUT | Input | End of Day Drill Depth | End of Day Bailing Depth | Bedrock | 10,000YBP Min | 10,000YBP Max | Able to Output | Drill Fluid Planned In | Drill Fluid Still Needed In | Ice Core Boxes Planned OUT | Ice Core Boxes Still Needed OUT | Baseline 1: Perfect Setup, 24hr Drilling. No Drilling, Weather, or Logistics Issues. No Burnout! Worst Case Scenario for Cargo Requirements
Start Date | 2025-11-10 | Mon | Open Camp | 12 | 0 | 0 | 0 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 | 0 | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-11 | Tue | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-12 | Wed | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-13 | Thu | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-14 | Fri | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-15 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-16 | Sun | REST | 0 | 0 | 0 | 0 | #VALUE! | 70 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 0 | 0 |  | 0 |  | -70 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-17 | Mon | Drilling | 8 | 8 | 8 | 480 | 79.8333 | 79.8333 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 1.6389 | 1.6389 | 1.6389 |  | 0 |  | -79.8333 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-18 | Tue | Drilling | 8 | 8 | 16 | 480 | 89.5102 | 89.5102 | 9.5102 | 0.63401 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 3.2517 | 1.6128 | 3.2517 |  | 0 |  | -89.5102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-19 | Wed | Drilling | 8 | 8 | 24 | 480 | 99.0379 | 99.0379 | 19.0379 | 1.2692 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4.8397 | 1.5879 | 4.8397 |  | 0 |  | -99.0379 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-20 | Thu | Drilling | 24 | 24 | 48 | 1440 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 |  | 4 |  | 6 | 9.4651 | 4.6254 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-11-21 | Fri | Drilling | 24 | 24 | 72 | 1440 | 153.4144 | 153.4144 | 73.4144 | 4.8943 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 13.9024 | 4.4373 | 13.9024 |  | 0 |  | -153.4144 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-22 | Sat | Drilling | 24 | 24 | 96 | 1440 | 179.0374 | 179.0374 | 99.0374 | 6.6025 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 18.1729 | 4.2705 | 18.1729 |  | 0 |  | -179.0374 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-23 | Sun | Drilling | 24 | 24 | 120 | 1440 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 22.2941 | 4.1212 | 22.2941 |  | 20 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105
| 2025-11-24 | Mon | REST | 0 | 0 | 120 | 0 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 22.2941 | 0 | 2.2941 |  | 0 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-25 | Tue | Drilling | 24 | 24 | 144 | 1440 | 227.6833 | 227.6833 | 147.6833 | 9.8456 | 0 | 0 | 0 | 0 |  | 10 |  | 6 | 26.2805 | 3.9865 | 6.2805 |  | 0 |  | -227.6833 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-11-26 | Wed | Drilling | 24 | 24 | 168 | 1440 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 30.1447 | 3.8642 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-27 | Thu | Drilling | 24 | 24 | 192 | 1440 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 33.8973 | 3.7525 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-28 | Fri | Drilling | 24 | 24 | 216 | 1440 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 37.5473 | 3.65 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-29 | Sat | Drilling | 24 | 24 | 240 | 1440 | 316.6164 | 316.6164 | 236.6164 | 15.7744 | 0 | 0 | 0 | 0 |  | 16 |  | 6 | 41.1027 | 3.5555 | 21.1027 |  | 20 |  | -316.6164 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | -105
| 2025-11-30 | Sun | Drilling | 24 | 24 | 264 | 1440 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 44.5706 | 3.4679 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-01 | Mon | REST | 0 | 0 | 264 | 0 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 44.5706 | 0 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-02 | Tue | Drilling | 24 | 24 | 288 | 1440 | 357.7428 | 357.7428 | 277.7428 | 18.5162 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 47.9571 | 3.3865 | 7.9571 |  | 0 |  | -357.7428 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-03 | Wed | Drilling | 24 | 24 | 312 | 1440 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 51.2677 | 3.3106 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-04 | Thu | Drilling | 24 | 24 | 336 | 1440 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 |  | 22 |  | 6 | 54.5073 | 3.2396 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-12-05 | Fri | Drilling | 24 | 24 | 360 | 1440 | 416.0811 | 416.0811 | 336.0811 | 22.4054 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 57.6802 | 3.1729 | 17.6802 |  | 0 |  | -416.0811 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-06 | Sat | Drilling | 24 | 24 | 384 | 1440 | 434.7424 | 434.7424 | 354.7424 | 23.6495 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 60.7904 | 3.1102 | 20.7904 |  | 20 |  | -434.7424 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105
| 2025-12-07 | Sun | Drilling | 24 | 24 | 408 | 1440 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 63.8415 | 3.0511 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-08 | Mon | REST | 0 | 0 | 408 | 0 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 63.8415 | 2.1316e-14 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-09 | Tue | Drilling | 24 | 24 | 432 | 1440 | 471.0203 | 471.0203 | 391.0203 | 26.068 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 66.8367 | 2.9952 | 6.8367 |  | 0 |  | -471.0203 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-10 | Wed | Drilling | 24 | 24 | 456 | 1440 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 |  | 28 |  | 6 | 69.779 | 2.9423 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-12-11 | Thu | Drilling | 24 | 24 | 480 | 1440 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 72.6712 | 2.8921 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-12 | Fri | Drilling | 24 | 24 | 504 | 1440 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 75.5156 | 2.8444 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-13 | Sat | Drilling | 24 | 24 | 528 | 1440 | 539.8871 | 539.8871 | 459.8871 | 30.6591 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 78.3145 | 2.799 | 18.3145 |  | 0 |  | -539.8871 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-14 | Sun | Drilling | 24 | 24 | 552 | 1440 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 81.0702 | 2.7557 | 21.0702 |  | 20 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105
| 2025-12-15 | Mon | REST | 0 | 0 | 552 | 0 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 81.0702 | 0 | 1.0702 |  | 0 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-16 | Tue | Drilling | 24 | 24 | 576 | 1440 | 572.7068 | 572.7068 | 492.7068 | 32.8471 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 83.7845 | 2.7143 | 3.7845 |  | 0 |  | -572.7068 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-17 | Wed | Drilling | 24 | 24 | 600 | 1440 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 |  | 34 |  | 6 | 86.4592 | 2.6747 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-12-18 | Thu | Drilling | 24 | 24 | 624 | 1440 | 604.5762 | 604.5762 | 524.5762 | 34.9717 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 89.096 | 2.6368 | 9.096 |  | 0 |  | -604.5762 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-19 | Fri | Drilling | 24 | 24 | 648 | 1440 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 91.6966 | 2.6005 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-20 | Sat | Drilling | 24 | 24 | 672 | 1440 | 635.5735 | 635.5735 | 555.5735 | 37.0382 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 94.2623 | 2.5657 | 14.2623 |  | 0 |  | -635.5735 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | TOTAL DRILLING | 36 | days | 816 | hrs
| 2025-12-21 | Sun | Drilling | 24 | 24 | 696 | 1440 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 96.7944 | 2.5322 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | TOTAL BAILING | 6 | days | 144 | hrs
| 2025-12-22 | Mon | REST | 0 | 0 | 696 | 0 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 96.7944 | 0 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-23 | Tue | Drilling | 24 | 24 | 720 | 1440 | 665.7666 | 665.7666 | 585.7666 | 39.0511 | 0 | 0 | 0 | 0 |  | 40 |  | 6 | 99.2944 | 2.5 | 19.2944 |  | 0 |  | -665.7666 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A | TOTAL WORKING | 54 | days | 1116 | hrs
| 2025-12-24 | Wed | Drilling | 24 | 24 | 744 | 1440 | 680.5804 | 680.5804 | 600.5804 | 40.0387 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 101.7634 | 2.469 | 21.7634 |  | 20 |  | -680.5804 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105 | TOTAL REST | 8 | days
| 2025-12-25 | Thu | Drilling | 24 | 24 | 768 | 1440 | 695.2149 | 695.2149 | 615.2149 | 41.0143 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 104.2025 | 2.4391 | 4.2025 |  | 0 |  | -695.2149 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-26 | Fri | REST | 0 | 0 | 768 | 0 | 695.2149 | 695.2149 | 615.2149 | 41.0143 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 104.2025 | 0 | 4.2025 |  | 0 |  | -695.2149 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | FIELD TIME | 62 | days
| 2025-12-27 | Sat | Drilling | 24 | 24 | 792 | 1440 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 106.6127 | 2.4103 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | SLACK | 22 | days
| 2025-12-28 | Sun | Drilling | 24 | 24 | 816 | 1440 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 0 | 0 | 0 | 80 | 46 |  | 0 | 108.9952 | 2.3824 | 8.9952 |  | 0 |  | -723.9711 | -80 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-29 | Mon | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 24 | 1440 | 259.4033 | 259.4033 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -259.4033 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-30 | Tue | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 48 | 1440 | 400.4713 | 400.4713 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-31 | Wed | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 72 | 1440 | 510.1938 | 510.1938 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -510.1938 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-01 | Thu | REST | 0 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 72 | 0 | 510.1938 | 510.1938 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -510.1938 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-02 | Fri | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 96 | 1440 | 603.2085 | 603.2085 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-03 | Sat | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 120 | 1440 | 685.4061 | 685.4061 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -685.4061 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-04 | Sun | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 144 | 1440 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-05 | Mon | Drill & Tent Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-06 | Tue | Drill & Tent Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-07 | Wed | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-08 | Thu | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-09 | Fri | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-10 | Sat | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-11 | Sun | Camp Closed | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | 0 | #N/A | #N/A | #N/A | #N/A
| 2026-01-12 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-13 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-14 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-15 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-16 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-17 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-18 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-19 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-20 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-21 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-22 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-23 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-24 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-25 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-26 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-27 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-28 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-29 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-30 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-31 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-01 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-02 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-03 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-04 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-05 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-06 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-07 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-08 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-09 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-10 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-11 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-12 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-13 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-14 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-15 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-16 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-17 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-18 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-19 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-20 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-21 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-22 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-23 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-24 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-25 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-26 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-27 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A

## Baseline 2 - Good, 16hr (hidden)
|  | Day | Drilling Critical Path | Working Day (hrs) | Drilling Day (hrs) | Cumulative Drilling Time (hrs) | Drilling Day (mins) | New Drilling Depth (m) | End of Day Drill Depth (m) | Drill Fluid Height (m) | Drill Fluid Used (Drums) | Bailing Day (hrs) | Cumulative Bailing Time (hrs) | Bailing Day (mins) | New Bailing Depth (m) | End of Day Bailing Depth (m) | Drill Fluid in Field (Drums) | Drill Fluid Planned Arrival (Drums) | Drill Fluid Still Required IN (Drums) | Ice Core Boxes Filled | Today's Ice Core Boxes Filled | Filled Ice Core Boxes in Field | Ice Core Boxes Planned Removal | Ice Core Box Flight Ready OUT | Input | End of Day Drill Depth | End of Day Bailing Depth | Bedrock | 10,000YBP Min | 10,000YBP Max | Able to Output | Drill Fluid Planned In | Drill Fluid Still Needed In | Ice Core Boxes Planned OUT | Ice Core Boxes Still Needed OUT | Baseline 2: Good Setup, 16hr Drilling. No Drilling, Weather, or Logistics Issues. My Best Hope for a Good Season
Start Date | 2025-11-10 | Mon | Open Camp | 12 | 0 | 0 | 0 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 | 0 | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-11 | Tue | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-12 | Wed | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-13 | Thu | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-14 | Fri | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-15 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-16 | Sun | REST |  | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-17 | Mon | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-18 | Tue | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-19 | Wed | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-20 | Thu | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-21 | Fri | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-22 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-23 | Sun | REST | 0 | 0 | 0 | 0 | #VALUE! | 70 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 0 | 0 |  | 0 |  | -70 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-24 | Mon | Drilling | 8 | 8 | 8 | 480 | 79.8333 | 79.8333 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 1.6389 | 1.6389 | 1.6389 |  | 0 |  | -79.8333 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-25 | Tue | Drilling | 8 | 8 | 16 | 480 | 89.5102 | 89.5102 | 9.5102 | 0.63401 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 3.2517 | 1.6128 | 3.2517 |  | 0 |  | -89.5102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-26 | Wed | Drilling | 8 | 8 | 24 | 480 | 99.0379 | 99.0379 | 19.0379 | 1.2692 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4.8397 | 1.5879 | 4.8397 |  | 0 |  | -99.0379 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-27 | Thu | Drilling | 16 | 16 | 40 | 960 | 117.672 | 117.672 | 37.672 | 2.5115 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 7.9453 | 3.1057 | 7.9453 |  | 0 |  | -117.672 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-28 | Fri | Drilling | 16 | 16 | 56 | 960 | 135.7837 | 135.7837 | 55.7837 | 3.7189 | 0 | 0 | 0 | 0 |  | 4 |  | 6 | 10.9639 | 3.0186 | 10.9639 |  | 0 |  | -135.7837 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-11-29 | Sat | Drilling | 16 | 16 | 72 | 960 | 153.4144 | 153.4144 | 73.4144 | 4.8943 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 13.9024 | 2.9385 | 13.9024 |  | 0 |  | -153.4144 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-11-30 | Sun | Drilling | 16 | 16 | 88 | 960 | 170.6008 | 170.6008 | 90.6008 | 6.0401 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 16.7668 | 2.8644 | 16.7668 |  | 0 |  | -170.6008 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-01 | Mon | Drilling | 16 | 16 | 104 | 960 | 187.3746 | 187.3746 | 107.3746 | 7.1583 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 19.5624 | 2.7956 | 19.5624 |  | 0 |  | -187.3746 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-02 | Tue | Drilling | 16 | 16 | 120 | 960 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 22.2941 | 2.7316 | 22.2941 |  | 20 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105
| 2025-12-03 | Wed | REST | 0 | 0 | 120 | 0 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 |  | 10 |  | 0 | 22.2941 | 0 | 2.2941 |  | 0 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-04 | Thu | Drilling | 16 | 16 | 136 | 960 | 219.7952 | 219.7952 | 139.7952 | 9.3197 | 0 | 0 | 0 | 0 |  | 10 |  | 6 | 24.9659 | 2.6718 | 4.9659 |  | 0 |  | -219.7952 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-12-05 | Fri | Drilling | 16 | 16 | 152 | 960 | 235.4898 | 235.4898 | 155.4898 | 10.366 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 27.5816 | 2.6158 | 7.5816 |  | 0 |  | -235.4898 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-06 | Sat | Drilling | 16 | 16 | 168 | 960 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 30.1447 | 2.5631 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-07 | Sun | Drilling | 16 | 16 | 184 | 960 | 265.9494 | 265.9494 | 185.9494 | 12.3966 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 32.6582 | 2.5135 | 12.6582 |  | 0 |  | -265.9494 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-08 | Mon | Drilling | 16 | 16 | 200 | 960 | 280.7495 | 280.7495 | 200.7495 | 13.3833 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 35.1249 | 2.4667 | 15.1249 |  | 0 |  | -280.7495 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-09 | Tue | Drilling | 16 | 16 | 216 | 960 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 37.5473 | 2.4224 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-10 | Wed | REST | 0 | 0 | 216 | 0 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 37.5473 | 0 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-11 | Thu | Drilling | 16 | 16 | 232 | 960 | 309.5658 | 309.5658 | 229.5658 | 15.3044 | 0 | 0 | 0 | 0 |  | 16 |  | 6 | 39.9276 | 2.3804 | 19.9276 |  | 0 |  | -309.5658 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-12-12 | Fri | Drilling | 16 | 16 | 248 | 960 | 323.6086 | 323.6086 | 243.6086 | 16.2406 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 42.2681 | 2.3405 | 22.2681 |  | 20 |  | -323.6086 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105
| 2025-12-13 | Sat | Drilling | 16 | 16 | 264 | 960 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 44.5706 | 2.3025 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-14 | Sun | Drilling | 16 | 16 | 280 | 960 | 351.0219 | 351.0219 | 271.0219 | 18.0681 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 46.837 | 2.2664 | 6.837 |  | 0 |  | -351.0219 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-15 | Mon | Drilling | 16 | 16 | 296 | 960 | 364.4131 | 364.4131 | 284.4131 | 18.9609 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 49.0688 | 2.2319 | 9.0688 |  | 0 |  | -364.4131 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-16 | Tue | Drilling | 16 | 16 | 312 | 960 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 51.2677 | 2.1989 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-17 | Wed | REST | 0 | 0 | 312 | 0 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 51.2677 | 0 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-18 | Thu | Drilling | 16 | 16 | 328 | 960 | 390.6102 | 390.6102 | 310.6102 | 20.7073 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 53.435 | 2.1673 | 13.435 |  | 0 |  | -390.6102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-19 | Fri | Drilling | 16 | 16 | 344 | 960 | 403.4326 | 403.4326 | 323.4326 | 21.5622 | 0 | 0 | 0 | 0 |  | 22 |  | 6 | 55.5721 | 2.1371 | 15.5721 |  | 0 |  | -403.4326 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-12-20 | Sat | Drilling | 16 | 16 | 360 | 960 | 416.0811 | 416.0811 | 336.0811 | 22.4054 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 57.6802 | 2.1081 | 17.6802 |  | 0 |  | -416.0811 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | TOTAL DRILLING | 52 | days | 808 | hrs
| 2025-12-21 | Sun | Drilling | 16 | 16 | 376 | 960 | 428.5624 | 428.5624 | 348.5624 | 23.2375 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 59.7604 | 2.0802 | 19.7604 |  | 0 |  | -428.5624 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | TOTAL BAILING | 6 | days | 144 | hrs
| 2025-12-22 | Mon | Drilling | 16 | 16 | 392 | 960 | 440.883 | 440.883 | 360.883 | 24.0589 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 61.8138 | 2.0534 | 21.8138 |  | 20 |  | -440.883 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105
| 2025-12-23 | Tue | Drilling | 16 | 16 | 408 | 960 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 63.8415 | 2.0277 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | TOTAL WORKING | 76 | days | 1180 | hrs
| 2025-12-24 | Wed | REST | 0 | 0 | 408 | 0 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 63.8415 | 0 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | TOTAL REST | 12 | days
| 2025-12-25 | Thu | Drilling | 16 | 16 | 424 | 960 | 465.066 | 465.066 | 385.066 | 25.6711 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 65.8443 | 2.0028 | 5.8443 |  | 0 |  | -465.066 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-26 | Fri | Drilling | 16 | 16 | 440 | 960 | 476.9394 | 476.9394 | 396.9394 | 26.4626 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 67.8232 | 1.9789 | 7.8232 |  | 0 |  | -476.9394 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | FIELD TIME | 88 | days
| 2025-12-27 | Sat | Drilling | 16 | 16 | 456 | 960 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 69.779 | 1.9558 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | SLACK | -4 | days
| 2025-12-28 | Sun | REST | 0 | 0 | 456 | 0 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 |  | 28 |  | 6 | 69.779 | 0 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2025-12-29 | Mon | Drilling | 16 | 16 | 472 | 960 | 500.2752 | 500.2752 | 420.2752 | 28.0183 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 71.7125 | 1.9335 | 11.7125 |  | 0 |  | -500.2752 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-30 | Tue | Drilling | 16 | 16 | 488 | 960 | 511.7468 | 511.7468 | 431.7468 | 28.7831 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 73.6245 | 1.9119 | 13.6245 |  | 0 |  | -511.7468 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2025-12-31 | Wed | Drilling | 16 | 16 | 504 | 960 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 75.5156 | 1.8911 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-01 | Thu | Drilling | 16 | 16 | 520 | 960 | 534.3187 | 534.3187 | 454.3187 | 30.2879 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 77.3864 | 1.8709 | 17.3864 |  | 0 |  | -534.3187 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-02 | Fri | Drilling | 16 | 16 | 536 | 960 | 545.4267 | 545.4267 | 465.4267 | 31.0284 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 79.2378 | 1.8513 | 19.2378 |  | 0 |  | -545.4267 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-03 | Sat | REST | 0 | 0 | 536 | 0 | 545.4267 | 545.4267 | 465.4267 | 31.0284 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 79.2378 | 0 | 19.2378 |  | 0 |  | -545.4267 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-04 | Sun | Drilling | 16 | 16 | 552 | 960 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 81.0702 | 1.8324 | 21.0702 |  | 20 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -105
| 2026-01-05 | Mon | Drilling | 16 | 16 | 568 | 960 | 567.3051 | 567.3051 | 487.3051 | 32.487 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 82.8842 | 1.814 | 2.8842 |  | 0 |  | -567.3051 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-06 | Tue | Drilling | 16 | 16 | 584 | 960 | 578.0821 | 578.0821 | 498.0821 | 33.2055 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 84.6803 | 1.7962 | 4.6803 |  | 0 |  | -578.0821 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-07 | Wed | REST | 0 | 0 | 584 | 0 | 578.0821 | 578.0821 | 498.0821 | 33.2055 | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 84.6803 | 0 | 4.6803 |  | 0 |  | -578.0821 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-08 | Thu | Drilling | 16 | 16 | 600 | 960 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 |  | 34 |  | 6 | 86.4592 | 1.7788 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | #N/A
| 2026-01-09 | Fri | Drilling | 16 | 16 | 616 | 960 | 599.3272 | 599.3272 | 519.3272 | 34.6218 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 88.2212 | 1.762 | 8.2212 |  | 0 |  | -599.3272 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-10 | Sat | Drilling | 16 | 16 | 632 | 960 | 609.801 | 609.801 | 529.801 | 35.3201 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 89.9668 | 1.7456 | 9.9668 |  | 0 |  | -609.801 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-11 | Sun | Drilling | 16 | 16 | 648 | 960 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 91.6966 | 1.7297 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-12 | Mon | Drilling | 16 | 16 | 664 | 960 | 630.4649 | 630.4649 | 550.4649 | 36.6977 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 93.4108 | 1.7142 | 13.4108 |  | 0 |  | -630.4649 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-13 | Tue | Drilling | 16 | 16 | 680 | 960 | 640.6598 | 640.6598 | 560.6598 | 37.3773 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 95.11 | 1.6992 | 15.11 |  | 0 |  | -640.6598 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-14 | Wed | REST | 0 | 0 | 680 | 0 | 640.6598 | 640.6598 | 560.6598 | 37.3773 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 95.11 | 0 | 15.11 |  | 0 |  | -640.6598 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-15 | Thu | Drilling | 16 | 16 | 696 | 960 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 96.7944 | 1.6845 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-16 | Fri | Drilling | 16 | 16 | 712 | 960 | 660.7876 | 660.7876 | 580.7876 | 38.7192 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 98.4646 | 1.6702 | 18.4646 |  | 0 |  | -660.7876 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-17 | Sat | Drilling | 16 | 16 | 728 | 960 | 670.7248 | 670.7248 | 590.7248 | 39.3817 | 0 | 0 | 0 | 0 |  | 40 |  | 6 | 100.1208 | 1.6562 | 20.1208 |  | 20 |  | -670.7248 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -35 | #N/A | -105
| 2026-01-18 | Sun | Drilling | 16 | 16 | 744 | 960 | 680.5804 | 680.5804 | 600.5804 | 40.0387 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 101.7634 | 1.6426 | 1.7634 |  | 0 |  | -680.5804 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-19 | Mon | Drilling | 16 | 16 | 760 | 960 | 690.3562 | 690.3562 | 610.3562 | 40.6904 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 103.3927 | 1.6293 | 3.3927 |  | 0 |  | -690.3562 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-20 | Tue | Drilling | 16 | 16 | 776 | 960 | 700.0543 | 700.0543 | 620.0543 | 41.337 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 105.0091 | 1.6163 | 5.0091 |  | 0 |  | -700.0543 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-21 | Wed | REST | 0 | 0 | 776 | 0 | 700.0543 | 700.0543 | 620.0543 | 41.337 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 105.0091 | 0 | 5.0091 |  | 0 |  | -700.0543 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-22 | Thu | Drilling | 16 | 16 | 792 | 960 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 |  | 46 |  | 0 | 106.6127 | 1.6037 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-23 | Fri | Drilling | 16 | 16 | 808 | 960 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 0 | 0 | 0 | 80 | 46 |  | 0 | 108.2041 | 1.5913 | 8.2041 |  | 0 |  | -719.2244 | -80 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-24 | Sat | Bailing | 24 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 24 | 24 | 1440 | 259.4033 | 259.4033 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -259.4033 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-25 | Sun | Bailing | 24 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 24 | 48 | 1440 | 400.4713 | 400.4713 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-26 | Mon | Bailing | 24 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 24 | 72 | 1440 | 510.1938 | 510.1938 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -510.1938 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-27 | Tue | Bailing | 24 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 24 | 96 | 1440 | 603.2085 | 603.2085 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-28 | Wed | REST | 0 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 96 | 0 | 603.2085 | 603.2085 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-29 | Thu | Bailing | 24 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 24 | 120 | 1440 | 685.4061 | 685.4061 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -685.4061 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-30 | Fri | Bailing | 24 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 24 | 144 | 1440 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-01-31 | Sat | Drill & Tent Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-01 | Sun | Drill & Tent Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-02 | Mon | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-03 | Tue | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-04 | Wed | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-05 | Thu | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-06 | Fri | Camp Closed | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | 0 | #N/A | #N/A | #N/A | #N/A
| 2026-02-07 | Sat |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-08 | Sun |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-09 | Mon |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-10 | Tue |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-11 | Wed |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-12 | Thu |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-13 | Fri |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-14 | Sat |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-15 | Sun |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-16 | Mon |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-17 | Tue |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-18 | Wed |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-19 | Thu |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-20 | Fri |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-21 | Sat |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-22 | Sun |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-23 | Mon |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-24 | Tue |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-25 | Wed |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-26 | Thu |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A
| 2026-02-27 | Fri |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 144 | 0 | 759.8619 | 759.8619 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -759.8619 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A

## 04-07-25-Scen3-Good,24-16hr
Date | Day | Drilling Critical Path | Working Day (hrs) | Drilling Day (hrs) | Cumulative Drilling Time (hrs) | Drilling Day (mins) | New Drilling Depth (m) | End of Day Drill Depth (m) | Drill Fluid Height (m) | Drill Fluid Used (Drums) | Bailing Day (hrs) | Cumulative Bailing Time (hrs) | Bailing Day (mins) | New Bailing Depth (m) | Cumulative Drill Fluid Recovered (Drums) | Daily Drill Fluid Recovered (Drums) | End of Day Bailing Depth (m) | Drilling/Bailing Fuel Burn (Drums) | Cumulative Drilling/Bailing Fuel Burn (Drums) | Drilling/Bailing Fuel in Field (Drums) | Drilling/Bailing Fuel Planned Arrival (Drums) | Fuel Still Required for Drilling/Bailing IN (Drums) | Drill Fluid in Field (Drums) | Drill Fluid Planned Arrival (Drums) | Drill Fluid Still Required IN (Drums) | Ice Core Boxes Filled | Today's Ice Core Boxes Filled | Filled Ice Core Boxes in Field | Ice Core Boxes Planned Removal | Ice Core Box Flight Ready OUT | Input | End of Day Drill Depth | End of Day Bailing Depth | Bedrock | 10,000YBP Min | 10,000YBP Max | Able to Output | Drilling Fuel Planned | Drilling Fuel Still Needed | Drill Fluid Planned In | Drill Fluid Still Needed In | Ice Core Boxes Planned OUT | Ice Core Boxes Still Needed OUT | Drilling Fuel in Camp | D60 in Camp (excl Borehole) | Filled Core Boxes in Camp | Scenario 3: Good Setup, 24->16hr Drilling. No Drilling, Weather, or Logistics Issues. My Best Hope for a Good Season | [6 empty] | How to use this Scenario Planner:
2025-11-12 | Wed | Open Camp | 12 | 0 | 0 | 0 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 | 0 | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 |  | Date | PAX |  |  | Date | PAX | This is an input cell |  | input | do not change values in any cell but these
2025-11-13 | Thu | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | First Input | 2025-11-12 | 5 |  | First Output | 2026-01-21 | 5 | Do not cut and paste cells as it will break the formulae that make this sheet work (you can copy though)
2025-11-14 | Fri | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | Second Input | 2025-11-17 | 5 |  | Second Output | 2026-02-02 | 5
2025-11-15 | Sat | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 1. Set the input and output dates (found above the charts)
2025-11-16 | Sun | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 2. Set drill, project, and logistics constraints in the "Drilling Spec" sheet.
2025-11-17 | Mon | REST | 0 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 3. Fill in the "Drilling Critical Path" and "Working Day (hrs)" columns with the activities that will be undertaken each day. There are special values you can put in "Drilling Critical Path" that will help - you must type them in without typos!
2025-11-18 | Tue | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-19 | Wed | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-20 | Thu | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | REST |  | counts as a rest day.
2025-11-21 | Fri | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Drilling |  | counts the hours towards drilling progress.
2025-11-22 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Bailing |  | counts the hours towards bailing progress.
2025-11-23 | Sun | REST | 0 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Camp Closed |  | notes when we're finished in camp.
2025-11-24 | Mon | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | The upper graph will show drilling and bailing progress given your inputted activities, ensure you reach target depth/bedrock!
2025-11-25 | Tue | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 4 |  | 0 | 0 | 0 | 0 |  | 0 |  | -70 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-26 | Wed | Drilling | 8 | 8 | 8 | 480 | 79.8333 | 79.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.16033 | 5.8397 |  | 0 | 4 |  | 0 | 1.6389 | 1.6389 | 1.6389 |  | 0 |  | -79.8333 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.8397 | 4 | 1.6389 | [8 empty] | Note: You need to consider yourself whether the inputted activities are realistic given the staffing available.
2025-11-27 | Thu | Drilling | 8 | 8 | 16 | 480 | 89.5102 | 89.5102 | 9.5102 | 0.63401 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.32065 | 5.6793 |  | 0 | 4 |  | 0 | 3.2517 | 1.6128 | 3.2517 |  | 0 |  | -89.5102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6793 | 3.366 | 3.2517
2025-11-28 | Fri | Drilling | 8 | 8 | 24 | 480 | 99.0379 | 99.0379 | 19.0379 | 1.2692 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.48098 | 5.519 |  | 0 | 4 |  | 0 | 4.8397 | 1.5879 | 4.8397 |  | 0 |  | -99.0379 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.519 | 2.7308 | 4.8397 | [8 empty] | The graph also will show crosses on the dates where logistic input is required to keep the planned schedule moving. For fuel and drilling fluid, crosses mark the last chance to get more in before drilling ops shut down. For ice core boxes crosses mark the earliest a full load of boxes would be ready for removal.
2025-11-29 | Sat | Drilling | 24 | 24 | 48 | 1440 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 0.96195 | 5.038 |  | 0 | 4 |  | 0 | 9.4651 | 4.6254 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.038 | 0.88064 | 9.4651
2025-11-30 | Sun | REST | 0 | 0 | 48 | 0 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.96195 | 5.038 |  | 0 | 4 |  | 6 | 9.4651 | 0 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.038 | 0.88064 | 9.4651
2025-12-01 | Mon | Drilling | 24 | 24 | 72 | 1440 | 153.4144 | 153.4144 | 73.4144 | 4.8943 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.4429 | 4.5571 |  | 0 | 10 |  | 0 | 13.9024 | 4.4373 | 13.9024 |  | 0 |  | -153.4144 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5571 | 5.1057 | 13.9024
2025-12-02 | Tue | Drilling | 24 | 24 | 96 | 1440 | 179.0374 | 179.0374 | 99.0374 | 6.6025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.9239 | 4.0761 |  | 0 | 10 |  | 0 | 18.1729 | 4.2705 | 18.1729 |  | 0 |  | -179.0374 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0761 | 3.3975 | 18.1729
2025-12-03 | Wed | Drilling | 24 | 24 | 120 | 1440 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.4049 | 3.5951 |  | 0 | 10 |  | 0 | 22.2941 | 4.1212 | 22.2941 |  | 20 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 3.5951 | 1.749 | 22.2941 | [8 empty] | Note: Drilling/Bailing fuel only counts what is needed for drilling ops, fuel for other camp activities should be considered separately.
2025-12-04 | Thu | Drilling | 24 | 24 | 144 | 1440 | 227.6833 | 227.6833 | 147.6833 | 9.8456 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.8859 | 3.1141 |  | 0 | 10 |  | 6 | 26.2805 | 3.9865 | 6.2805 |  | 0 |  | -227.6833 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 3.1141 | 0.15445 | 6.2805
2025-12-05 | Fri | Drilling | 24 | 24 | 168 | 1440 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.3668 | 2.6332 |  | 0 | 16 |  | 0 | 30.1447 | 3.8642 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.6332 | 4.6088 | 10.1447 | [7 empty] | 4. Schedule deliveries of fuel and drill fluid, and pickup of ice core boxes. Use the "Drilling/Bailing Fuel Planned Arrival (Drums)", " Drill Fluid Planned Arrival (Drums)", and "Ice Core Boxes Planned Removal" columns for this. These will be marked on the graph as circles, and the cross showing needs that remain unscheduled will update automatically.
2025-12-06 | Sat | Drilling | 24 | 24 | 192 | 1440 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.8478 | 2.1522 |  | 0 | 16 |  | 0 | 33.8973 | 3.7525 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1522 | 3.1078 | 13.8973
2025-12-07 | Sun | REST | 0 | 0 | 192 | 0 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.8478 | 2.1522 |  | 0 | 16 |  | 0 | 33.8973 | 0 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1522 | 3.1078 | 13.8973
2025-12-08 | Mon | Drilling | 24 | 24 | 216 | 1440 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.3288 | 1.6712 |  | 0 | 16 |  | 0 | 37.5473 | 3.65 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6712 | 1.6478 | 17.5473
2025-12-09 | Tue | Drilling | 24 | 24 | 240 | 1440 | 316.6164 | 316.6164 | 236.6164 | 15.7744 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.8098 | 1.1902 |  | 0 | 16 |  | 6 | 41.1027 | 3.5555 | 21.1027 |  | 20 |  | -316.6164 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | -216 | 1.1902 | 0.22557 | 21.1027
2025-12-10 | Wed | Drilling | 24 | 24 | 264 | 1440 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.2907 | 0.70927 |  | 0 | 22 |  | 0 | 44.5706 | 3.4679 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.70927 | 4.8384 | 4.5706 | [8 empty] | The totals of these 'consumables' in camp are shown in the lower graph. (Note drilling fluid in the borehole is excluded).
2025-12-11 | Thu | Drilling | 24 | 24 | 288 | 1440 | 357.7428 | 357.7428 | 277.7428 | 18.5162 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.7717 | 0.22829 |  | 6 | 22 |  | 0 | 47.9571 | 3.3865 | 7.9571 |  | 0 |  | -357.7428 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.22829 | 3.4838 | 7.9571
2025-12-12 | Fri | Drilling | 24 | 24 | 312 | 1440 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.2527 | 5.7473 |  | 0 | 22 |  | 0 | 51.2677 | 3.3106 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7473 | 2.1596 | 11.2677 | [8 empty] | Note: Check the "Filled Ice Core Boxes in Field" column to avoid scheduling removing more core boxes than you have ready!
2025-12-13 | Sat | Drilling | 24 | 24 | 336 | 1440 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.7337 | 5.2663 |  | 0 | 22 |  | 0 | 54.5073 | 3.2396 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.2663 | 0.86376 | 14.5073
2025-12-14 | Sun | REST | 0 | 0 | 336 | 0 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.7337 | 5.2663 |  | 0 | 22 |  | 6 | 54.5073 | 2.1316e-14 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.2663 | 0.86376 | 14.5073 | [7 empty] | 5. Assess feasibility of the planned season (logistic demands realistic, enough PAX in field, enough time for issues and bad weather, rest periods in long seasons, room for other non-drilling activities, etc)
2025-12-15 | Mon | Drilling | 24 | 24 | 360 | 1440 | 416.0811 | 416.0811 | 336.0811 | 22.4054 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.2146 | 4.7854 |  | 0 | 28 |  | 0 | 57.6802 | 3.1729 | 17.6802 |  | 0 |  | -416.0811 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.7854 | 5.5946 | 17.6802
2025-12-16 | Tue | Drilling | 24 | 24 | 384 | 1440 | 434.7424 | 434.7424 | 354.7424 | 23.6495 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.6956 | 4.3044 |  | 0 | 28 |  | 0 | 60.7904 | 3.1102 | 20.7904 |  | 20 |  | -434.7424 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.3044 | 4.3505 | 20.7904
2025-12-17 | Wed | Drilling | 24 | 24 | 408 | 1440 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.1766 | 3.8234 |  | 0 | 28 |  | 0 | 63.8415 | 3.0511 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.8234 | 3.1301 | 3.8415 | [7 empty] | 6. Assess getting everything out again after! There'll be a lot of recovered drill fluid in drums…
2025-12-18 | Thu | Drilling | 24 | 24 | 432 | 1440 | 471.0203 | 471.0203 | 391.0203 | 26.068 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.6576 | 3.3424 |  | 0 | 28 |  | 0 | 66.8367 | 2.9952 | 6.8367 |  | 0 |  | -471.0203 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3424 | 1.932 | 6.8367
2025-12-19 | Fri | Drilling | 24 | 24 | 456 | 1440 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.1385 | 2.8615 |  | 0 | 28 |  | 6 | 69.779 | 2.9423 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 2.8615 | 0.75505 | 9.779
2025-12-20 | Sat | Drilling | 24 | 24 | 480 | 1440 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.6195 | 2.3805 |  | 0 | 34 |  | 0 | 72.6712 | 2.8921 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3805 | 5.5982 | 12.6712
2025-12-21 | Sun | REST | 0 | 0 | 480 | 0 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9.6195 | 2.3805 |  | 0 | 34 |  | 0 | 72.6712 | 0 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3805 | 5.5982 | 12.6712
2025-12-22 | Mon | Drilling | 24 | 24 | 504 | 1440 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.1005 | 1.8995 |  | 0 | 34 |  | 0 | 75.5156 | 2.8444 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8995 | 4.4604 | 15.5156
2025-12-23 | Tue | Drilling | 24 | 24 | 528 | 1440 | 539.8871 | 539.8871 | 459.8871 | 30.6591 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.5815 | 1.4185 |  | 0 | 34 |  | 0 | 78.3145 | 2.799 | 18.3145 |  | 0 |  | -539.8871 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4185 | 3.3409 | 18.3145
2025-12-24 | Wed | Drilling | 24 | 24 | 552 | 1440 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.0624 | 0.93756 |  | 0 | 34 |  | 0 | 81.0702 | 2.7557 | 21.0702 |  | 20 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 0.93756 | 2.2386 | 21.0702
2025-12-25 | Thu | REST | 0 | 0 | 552 | 0 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 11.0624 | 0.93756 |  | 0 | 34 |  | 0 | 81.0702 | 0 | 1.0702 |  | 0 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.93756 | 2.2386 | 1.0702 | TOTAL DRILLING | 41 | days | 824 | hrs
2025-12-26 | Fri | Drilling | 24 | 24 | 576 | 1440 | 572.7068 | 572.7068 | 492.7068 | 32.8471 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.5434 | 0.45659 |  | 6 | 34 |  | 0 | 83.7845 | 2.7143 | 3.7845 |  | 0 |  | -572.7068 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.45659 | 1.1529 | 3.7845 | TOTAL BAILING | 6 | days | 132 | hrs
2025-12-27 | Sat | Drilling | 24 | 24 | 600 | 1440 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.0244 | 5.9756 |  | 0 | 34 |  | 6 | 86.4592 | 2.6747 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.9756 | 0.082991 | 6.4592
2025-12-28 | Sun | Drilling | 16 | 16 | 616 | 960 | 599.3272 | 599.3272 | 519.3272 | 34.6218 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.345 | 5.655 |  | 0 | 40 |  | 0 | 88.2212 | 1.762 | 8.2212 |  | 0 |  | -599.3272 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.655 | 5.3782 | 8.2212 | TOTAL WORKING | 65 | days | 1184 | hrs
2025-12-29 | Mon | Drilling | 16 | 16 | 632 | 960 | 609.801 | 609.801 | 529.801 | 35.3201 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.6657 | 5.3343 |  | 0 | 40 |  | 0 | 89.9668 | 1.7456 | 9.9668 |  | 0 |  | -609.801 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3343 | 4.6799 | 9.9668 | TOTAL REST | 10 | days
2025-12-30 | Tue | Drilling | 16 | 16 | 648 | 960 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.9863 | 5.0137 |  | 0 | 40 |  | 0 | 91.6966 | 1.7297 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 3.988 | 11.6966
2025-12-31 | Wed | REST | 0 | 0 | 648 | 0 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.9863 | 5.0137 |  | 0 | 40 |  | 0 | 91.6966 | 0 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 3.988 | 11.6966 | FIELD TIME | 75 | days
2026-01-01 | Thu | Drilling | 16 | 16 | 664 | 960 | 630.4649 | 630.4649 | 550.4649 | 36.6977 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.307 | 4.693 |  | 0 | 40 |  | 0 | 93.4108 | 1.7142 | 13.4108 |  | 0 |  | -630.4649 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.693 | 3.3023 | 13.4108 | SLACK | 7 | days
2026-01-02 | Fri | Drilling | 16 | 16 | 680 | 960 | 640.6598 | 640.6598 | 560.6598 | 37.3773 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.6276 | 4.3724 |  | 0 | 40 |  | 0 | 95.11 | 1.6992 | 15.11 |  | 0 |  | -640.6598 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3724 | 2.6227 | 15.11
2026-01-03 | Sat | Drilling | 16 | 16 | 696 | 960 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.9483 | 4.0517 |  | 0 | 40 |  | 0 | 96.7944 | 1.6845 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 1.9489 | 16.7944
2026-01-04 | Sun | REST | 0 | 0 | 696 | 0 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13.9483 | 4.0517 |  | 0 | 40 |  | 0 | 96.7944 | 0 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 1.9489 | 16.7944
2026-01-05 | Mon | Drilling | 16 | 16 | 712 | 960 | 660.7876 | 660.7876 | 580.7876 | 38.7192 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.2689 | 3.7311 |  | 0 | 40 |  | 0 | 98.4646 | 1.6702 | 18.4646 |  | 0 |  | -660.7876 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.7311 | 1.2808 | 18.4646
2026-01-06 | Tue | Drilling | 16 | 16 | 728 | 960 | 670.7248 | 670.7248 | 590.7248 | 39.3817 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.5896 | 3.4104 |  | 0 | 40 |  | 6 | 100.1208 | 1.6562 | 20.1208 |  | 20 |  | -670.7248 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | -216 | 3.4104 | 0.61834 | 20.1208
2026-01-07 | Wed | Drilling | 16 | 16 | 744 | 960 | 680.5804 | 680.5804 | 600.5804 | 40.0387 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.9102 | 3.0898 |  | 0 | 46 |  | 0 | 101.7634 | 1.6426 | 1.7634 |  | 0 |  | -680.5804 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.0898 | 5.9613 | 1.7634
2026-01-08 | Thu | Drilling | 16 | 16 | 760 | 960 | 690.3562 | 690.3562 | 610.3562 | 40.6904 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.2309 | 2.7691 |  | 0 | 46 |  | 0 | 103.3927 | 1.6293 | 3.3927 |  | 0 |  | -690.3562 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.7691 | 5.3096 | 3.3927
2026-01-09 | Fri | Drilling | 16 | 16 | 776 | 960 | 700.0543 | 700.0543 | 620.0543 | 41.337 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.5515 | 2.4485 |  | 0 | 46 |  | 0 | 105.0091 | 1.6163 | 5.0091 |  | 0 |  | -700.0543 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.4485 | 4.663 | 5.0091
2026-01-10 | Sat | Drilling | 16 | 16 | 792 | 960 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.8722 | 2.1278 |  | 0 | 46 |  | 0 | 106.6127 | 1.6037 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1278 | 4.0216 | 6.6127
2026-01-11 | Sun | REST | 0 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 15.8722 | 2.1278 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1278 | 4.0216 | 6.6127
2026-01-12 | Mon | Drilling | 16 | 16 | 808 | 960 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 16.1928 | 1.8072 |  | 0 | 46 |  | 0 | 108.2041 | 1.5913 | 8.2041 |  | 0 |  | -719.2244 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8072 | 3.385 | 8.2041
2026-01-13 | Tue | Drilling | 16 | 16 | 824 | 960 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0.32065 | 16.5135 | 1.4865 |  | 0 | 46 |  | 0 | 109.7833 | 1.5792 | 9.7833 |  | 0 |  | -728.6998 | -80 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4865 | 2.7533 | 9.7833
2026-01-14 | Wed | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 24 | 1440 | 259.4033 | 10.7642 | 10.7642 | 259.4033 | 0.58537 | 17.0989 | 0.90114 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -259.4033 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.90114 | 13.5175 | 9.7833
2026-01-15 | Thu | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 48 | 1440 | 400.4713 | 19.2283 | 8.4641 | 400.4713 | 0.58537 | 17.6842 | 0.31577 |  | 6 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.31577 | 21.9816 | 9.7833
2026-01-16 | Fri | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 72 | 1440 | 510.1938 | 25.8116 | 6.5834 | 510.1938 | 0.58537 | 18.2696 | 5.7304 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -510.1938 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7304 | 28.565 | 9.7833
2026-01-17 | Sat | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 96 | 1440 | 603.2085 | 31.3925 | 5.5809 | 603.2085 | 0.58537 | 18.855 | 5.145 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.145 | 34.1459 | 9.7833
2026-01-18 | Sun | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 120 | 1440 | 685.4061 | 36.3244 | 4.9319 | 685.4061 | 0.58537 | 19.4403 | 4.5597 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -685.4061 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5597 | 39.0777 | 9.7833
2026-01-19 | Mon | Bailing | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 12 | 132 | 720 | 723.4668 | 38.608 | 2.2836 | 723.4668 | 0.29268 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 9.7833
2026-01-20 | Tue | Drill & Tent Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 9.7833
2026-01-21 | Wed | Drill & Tent Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 9.7833
2026-01-22 | Thu | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 9.7833
2026-01-23 | Fri | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 9.7833
2026-01-24 | Sat | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 9.7833
2026-01-25 | Sun | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 9.7833
2026-01-26 | Mon | Camp Closed | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 9.7833 |  | 9.7833 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.267 | 41.3614 | 9.7833
2026-01-27 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-01-28 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-01-29 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-01-30 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-01-31 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-01 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-02 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-03 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-04 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-05 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-06 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-07 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-08 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-09 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-10 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-11 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-12 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-13 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-14 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-15 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-16 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-17 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-18 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-19 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-20 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-21 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-22 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-23 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-24 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-25 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-26 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-27 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-02-28 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
2026-03-01 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 4.267 |  | 0 | 46 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.267 | 41.3614 | 0
Formulas:
Date = [Date, row above]+1

## 04-07-25-Scen4-ExFrontloadCargo
Date | Day | Drilling Critical Path | Working Day (hrs) | Drilling Day (hrs) | Cumulative Drilling Time (hrs) | Drilling Day (mins) | New Drilling Depth (m) | End of Day Drill Depth (m) | Drill Fluid Height (m) | Drill Fluid Used (Drums) | Bailing Day (hrs) | Cumulative Bailing Time (hrs) | Bailing Day (mins) | New Bailing Depth (m) | Cumulative Drill Fluid Recovered (Drums) | Daily Drill Fluid Recovered (Drums) | End of Day Bailing Depth (m) | Drilling/Bailing Fuel Burn (Drums) | Cumulative Drilling/Bailing Fuel Burn (Drums) | Drilling/Bailing Fuel in Field (Drums) | Drilling/Bailing Fuel Planned Arrival (Drums) | Fuel Still Required for Drilling/Bailing IN (Drums) | Drill Fluid in Field (Drums) | Drill Fluid Planned Arrival (Drums) | Drill Fluid Still Required IN (Drums) | Ice Core Boxes Filled | Today's Ice Core Boxes Filled | Filled Ice Core Boxes in Field | Ice Core Boxes Planned Removal | Ice Core Box Flight Ready OUT | Input | End of Day Drill Depth | End of Day Bailing Depth | Bedrock | 10,000YBP Min | 10,000YBP Max | Able to Output | Drilling Fuel Planned | Drilling Fuel Still Needed | Drill Fluid Planned In | Drill Fluid Still Needed In | Ice Core Boxes Planned OUT | Ice Core Boxes Still Needed OUT | Drilling Fuel in Camp | D60 in Camp (excl Borehole) | Filled Core Boxes in Camp | Scenario 4: As Scenario 3, but with some front-loading of fuel and drill fluid. | [6 empty] | How to use this Scenario Planner:
2025-11-12 | Wed | Open Camp | 12 | 0 | 0 | 0 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 | 0 | #N/A | #N/A | -720 | -624 | -688 | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 |  | Date | PAX |  |  | Date | PAX | This is an input cell |  | input | do not change values in any cell but these
2025-11-13 | Thu | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 4 | 0 | First Input | 2025-11-12 | 5 |  | First Output | 2026-01-21 | 5 | Do not cut and paste cells as it will break the formulae that make this sheet work (you can copy though)
2025-11-14 | Fri | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 6 | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 4 | 0 | Second Input | 2025-11-17 | 5 |  | Second Output | 2026-02-02 | 5
2025-11-15 | Sat | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 7 | 1 | 0 | 9 | 5 | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | -72 | #N/A | -144 | #N/A | #N/A | #N/A | 7 | 9 | 0 | [7 empty] | 1. Set the input and output dates (found above the charts)
2025-11-16 | Sun | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 15 | 6 | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | #N/A | 8 | 15 | 0 | [7 empty] | 2. Set drill, project, and logistics constraints in the "Drilling Spec" sheet.
2025-11-17 | Mon | REST | 0 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 15 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | 15 | 0 | [7 empty] | 3. Fill in the "Drilling Critical Path" and "Working Day (hrs)" columns with the activities that will be undertaken each day. There are special values you can put in "Drilling Critical Path" that will help - you must type them in without typos!
2025-11-18 | Tue | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 15 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | 15 | 0
2025-11-19 | Wed | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 15 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | 15 | 0
2025-11-20 | Thu | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 21 | 6 | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | #N/A | 8 | 21 | 0 | [8 empty] | REST |  | counts as a rest day.
2025-11-21 | Fri | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 21 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | 21 | 0 | [8 empty] | Drilling |  | counts the hours towards drilling progress.
2025-11-22 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 21 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | 21 | 0 | [8 empty] | Bailing |  | counts the hours towards bailing progress.
2025-11-23 | Sun | REST | 0 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 21 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | 21 | 0 | [8 empty] | Camp Closed |  | notes when we're finished in camp.
2025-11-24 | Mon | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 21 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | 21 | 0 | [8 empty] | The upper graph will show drilling and bailing progress given your inputted activities, ensure you reach target depth/bedrock!
2025-11-25 | Tue | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 |  | 0 | 27 | 6 | 0 | 0 | 0 | 0 |  | 0 |  | -70 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | #N/A | 8 | 27 | 0
2025-11-26 | Wed | Drilling | 8 | 8 | 8 | 480 | 79.8333 | 79.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.16033 | 7.8397 |  | 0 | 27 |  | 0 | 1.6389 | 1.6389 | 1.6389 |  | 0 |  | -79.8333 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.8397 | 27 | 1.6389 | [8 empty] | Note: You need to consider yourself whether the inputted activities are realistic given the staffing available.
2025-11-27 | Thu | Drilling | 8 | 8 | 16 | 480 | 89.5102 | 89.5102 | 9.5102 | 0.63401 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.32065 | 7.6793 |  | 0 | 27 |  | 0 | 3.2517 | 1.6128 | 3.2517 |  | 0 |  | -89.5102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.6793 | 26.366 | 3.2517
2025-11-28 | Fri | Drilling | 8 | 8 | 24 | 480 | 99.0379 | 99.0379 | 19.0379 | 1.2692 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.48098 | 7.519 |  | 0 | 27 |  | 0 | 4.8397 | 1.5879 | 4.8397 |  | 0 |  | -99.0379 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.519 | 25.7308 | 4.8397 | [8 empty] | The graph also will show crosses on the dates where logistic input is required to keep the planned schedule moving. For fuel and drilling fluid, crosses mark the last chance to get more in before drilling ops shut down. For ice core boxes crosses mark the earliest a full load of boxes would be ready for removal.
2025-11-29 | Sat | Drilling | 24 | 24 | 48 | 1440 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 0.96195 | 7.038 |  | 0 | 27 |  | 0 | 9.4651 | 4.6254 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.038 | 23.8806 | 9.4651
2025-11-30 | Sun | REST | 0 | 0 | 48 | 0 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.96195 | 7.038 |  | 0 | 27 |  | 0 | 9.4651 | 0 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.038 | 23.8806 | 9.4651
2025-12-01 | Mon | Drilling | 24 | 24 | 72 | 1440 | 153.4144 | 153.4144 | 73.4144 | 4.8943 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.4429 | 6.5571 |  | 0 | 27 |  | 0 | 13.9024 | 4.4373 | 13.9024 |  | 0 |  | -153.4144 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.5571 | 22.1057 | 13.9024
2025-12-02 | Tue | Drilling | 24 | 24 | 96 | 1440 | 179.0374 | 179.0374 | 99.0374 | 6.6025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.9239 | 6.0761 |  | 0 | 27 |  | 0 | 18.1729 | 4.2705 | 18.1729 |  | 0 |  | -179.0374 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.0761 | 20.3975 | 18.1729
2025-12-03 | Wed | Drilling | 24 | 24 | 120 | 1440 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.4049 | 5.5951 | 6 | 0 | 27 |  | 0 | 22.2941 | 4.1212 | 2.2941 | 20 | 0 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | -72 | #N/A | #N/A | #N/A | -216 | #N/A | 5.5951 | 18.749 | 2.2941 | [8 empty] | Note: Drilling/Bailing fuel only counts what is needed for drilling ops, fuel for other camp activities should be considered separately.
2025-12-04 | Thu | Drilling | 24 | 24 | 144 | 1440 | 227.6833 | 227.6833 | 147.6833 | 9.8456 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.8859 | 11.1141 |  | 0 | 27 |  | 0 | 26.2805 | 3.9865 | 6.2805 |  | 0 |  | -227.6833 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.1141 | 17.1544 | 6.2805
2025-12-05 | Fri | Drilling | 24 | 24 | 168 | 1440 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.3668 | 10.6332 |  | 0 | 27 |  | 0 | 30.1447 | 3.8642 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.6332 | 15.6088 | 10.1447 | [7 empty] | 4. Schedule deliveries of fuel and drill fluid, and pickup of ice core boxes. Use the "Drilling/Bailing Fuel Planned Arrival (Drums)", " Drill Fluid Planned Arrival (Drums)", and "Ice Core Boxes Planned Removal" columns for this. These will be marked on the graph as circles, and the cross showing needs that remain unscheduled will update automatically.
2025-12-06 | Sat | Drilling | 24 | 24 | 192 | 1440 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.8478 | 10.1522 |  | 0 | 27 |  | 0 | 33.8973 | 3.7525 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.1522 | 14.1078 | 13.8973
2025-12-07 | Sun | REST | 0 | 0 | 192 | 0 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.8478 | 10.1522 |  | 0 | 27 |  | 0 | 33.8973 | 0 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.1522 | 14.1078 | 13.8973
2025-12-08 | Mon | Drilling | 24 | 24 | 216 | 1440 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.3288 | 9.6712 |  | 0 | 27 |  | 0 | 37.5473 | 3.65 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.6712 | 12.6478 | 17.5473
2025-12-09 | Tue | Drilling | 24 | 24 | 240 | 1440 | 316.6164 | 316.6164 | 236.6164 | 15.7744 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.8098 | 9.1902 |  | 0 | 33 | 6 | 0 | 41.1027 | 3.5555 | 1.1027 | 20 | 0 |  | -316.6164 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | -144 | #N/A | -216 | #N/A | 9.1902 | 17.2256 | 1.1027
2025-12-10 | Wed | Drilling | 24 | 24 | 264 | 1440 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.2907 | 8.7093 |  | 0 | 33 |  | 0 | 44.5706 | 3.4679 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.7093 | 15.8384 | 4.5706 | [8 empty] | The totals of these 'consumables' in camp are shown in the lower graph. (Note drilling fluid in the borehole is excluded).
2025-12-11 | Thu | Drilling | 24 | 24 | 288 | 1440 | 357.7428 | 357.7428 | 277.7428 | 18.5162 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.7717 | 8.2283 |  | 0 | 33 |  | 0 | 47.9571 | 3.3865 | 7.9571 |  | 0 |  | -357.7428 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.2283 | 14.4838 | 7.9571
2025-12-12 | Fri | Drilling | 24 | 24 | 312 | 1440 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.2527 | 7.7473 |  | 0 | 33 |  | 0 | 51.2677 | 3.3106 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.7473 | 13.1596 | 11.2677 | [8 empty] | Note: Check the "Filled Ice Core Boxes in Field" column to avoid scheduling removing more core boxes than you have ready!
2025-12-13 | Sat | Drilling | 24 | 24 | 336 | 1440 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.7337 | 7.2663 |  | 0 | 33 |  | 0 | 54.5073 | 3.2396 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.2663 | 11.8638 | 14.5073
2025-12-14 | Sun | REST | 0 | 0 | 336 | 0 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.7337 | 7.2663 |  | 0 | 33 |  | 0 | 54.5073 | 2.1316e-14 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.2663 | 11.8638 | 14.5073 | [7 empty] | 5. Assess feasibility of the planned season (logistic demands realistic, enough PAX in field, enough time for issues and bad weather, rest periods in long seasons, room for other non-drilling activities, etc)
2025-12-15 | Mon | Drilling | 24 | 24 | 360 | 1440 | 416.0811 | 416.0811 | 336.0811 | 22.4054 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.2146 | 6.7854 |  | 0 | 33 |  | 0 | 57.6802 | 3.1729 | 17.6802 |  | 0 |  | -416.0811 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.7854 | 10.5946 | 17.6802
2025-12-16 | Tue | Drilling | 24 | 24 | 384 | 1440 | 434.7424 | 434.7424 | 354.7424 | 23.6495 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.6956 | 6.3044 | 4 | 0 | 35 | 2 | 0 | 60.7904 | 3.1102 | 0.79039 | 20 | 0 |  | -434.7424 | #N/A | -720 | -624 | -688 | #N/A | -72 | #N/A | -144 | #N/A | -216 | #N/A | 6.3044 | 11.3505 | 0.79039
2025-12-17 | Wed | Drilling | 24 | 24 | 408 | 1440 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.1766 | 9.8234 |  | 0 | 35 |  | 0 | 63.8415 | 3.0511 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.8234 | 10.1301 | 3.8415 | [7 empty] | 6. Assess getting everything out again after! There'll be a lot of recovered drill fluid in drums…
2025-12-18 | Thu | Drilling | 24 | 24 | 432 | 1440 | 471.0203 | 471.0203 | 391.0203 | 26.068 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.6576 | 9.3424 |  | 0 | 35 |  | 0 | 66.8367 | 2.9952 | 6.8367 |  | 0 |  | -471.0203 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.3424 | 8.932 | 6.8367
2025-12-19 | Fri | Drilling | 24 | 24 | 456 | 1440 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.1385 | 8.8615 |  | 0 | 35 |  | 0 | 69.779 | 2.9423 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.8615 | 7.7551 | 9.779
2025-12-20 | Sat | Drilling | 24 | 24 | 480 | 1440 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.6195 | 8.3805 |  | 0 | 35 |  | 0 | 72.6712 | 2.8921 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3805 | 6.5982 | 12.6712
2025-12-21 | Sun | REST | 0 | 0 | 480 | 0 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9.6195 | 8.3805 |  | 0 | 35 |  | 0 | 72.6712 | 0 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3805 | 6.5982 | 12.6712
2025-12-22 | Mon | Drilling | 24 | 24 | 504 | 1440 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.1005 | 7.8995 |  | 0 | 35 |  | 0 | 75.5156 | 2.8444 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.8995 | 5.4604 | 15.5156
2025-12-23 | Tue | Drilling | 24 | 24 | 528 | 1440 | 539.8871 | 539.8871 | 459.8871 | 30.6591 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.5815 | 7.4185 |  | 0 | 35 |  | 0 | 78.3145 | 2.799 | 18.3145 |  | 0 |  | -539.8871 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.4185 | 4.3409 | 18.3145
2025-12-24 | Wed | Drilling | 24 | 24 | 552 | 1440 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.0624 | 6.9376 |  | 0 | 41 | 6 | 0 | 81.0702 | 2.7557 | 1.0702 | 20 | 0 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | -144 | #N/A | -216 | #N/A | 6.9376 | 9.2386 | 1.0702
2025-12-25 | Thu | REST | 0 | 0 | 552 | 0 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 11.0624 | 6.9376 |  | 0 | 41 |  | 0 | 81.0702 | 0 | 1.0702 |  | 0 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.9376 | 9.2386 | 1.0702 | TOTAL DRILLING | 41 | days | 824 | hrs
2025-12-26 | Fri | Drilling | 24 | 24 | 576 | 1440 | 572.7068 | 572.7068 | 492.7068 | 32.8471 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.5434 | 6.4566 |  | 0 | 41 |  | 0 | 83.7845 | 2.7143 | 3.7845 |  | 0 |  | -572.7068 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.4566 | 8.1529 | 3.7845 | TOTAL BAILING | 6 | days | 132 | hrs
2025-12-27 | Sat | Drilling | 24 | 24 | 600 | 1440 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.0244 | 5.9756 |  | 0 | 41 |  | 0 | 86.4592 | 2.6747 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.9756 | 7.083 | 6.4592
2025-12-28 | Sun | Drilling | 16 | 16 | 616 | 960 | 599.3272 | 599.3272 | 519.3272 | 34.6218 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.345 | 5.655 |  | 0 | 41 |  | 0 | 88.2212 | 1.762 | 8.2212 |  | 0 |  | -599.3272 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.655 | 6.3782 | 8.2212 | TOTAL WORKING | 65 | days | 1184 | hrs
2025-12-29 | Mon | Drilling | 16 | 16 | 632 | 960 | 609.801 | 609.801 | 529.801 | 35.3201 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.6657 | 5.3343 |  | 0 | 41 |  | 0 | 89.9668 | 1.7456 | 9.9668 |  | 0 |  | -609.801 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3343 | 5.6799 | 9.9668 | TOTAL REST | 10 | days
2025-12-30 | Tue | Drilling | 16 | 16 | 648 | 960 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.9863 | 5.0137 |  | 0 | 41 |  | 0 | 91.6966 | 1.7297 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 4.988 | 11.6966
2025-12-31 | Wed | REST | 0 | 0 | 648 | 0 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.9863 | 5.0137 |  | 0 | 41 |  | 0 | 91.6966 | 0 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 4.988 | 11.6966 | FIELD TIME | 75 | days
2026-01-01 | Thu | Drilling | 16 | 16 | 664 | 960 | 630.4649 | 630.4649 | 550.4649 | 36.6977 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.307 | 4.693 |  | 0 | 41 |  | 0 | 93.4108 | 1.7142 | 13.4108 |  | 0 |  | -630.4649 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.693 | 4.3023 | 13.4108 | SLACK | 7 | days
2026-01-02 | Fri | Drilling | 16 | 16 | 680 | 960 | 640.6598 | 640.6598 | 560.6598 | 37.3773 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.6276 | 4.3724 |  | 0 | 41 |  | 0 | 95.11 | 1.6992 | 15.11 |  | 0 |  | -640.6598 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3724 | 3.6227 | 15.11
2026-01-03 | Sat | Drilling | 16 | 16 | 696 | 960 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.9483 | 4.0517 |  | 0 | 41 |  | 0 | 96.7944 | 1.6845 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 2.9489 | 16.7944
2026-01-04 | Sun | REST | 0 | 0 | 696 | 0 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13.9483 | 4.0517 |  | 0 | 41 |  | 0 | 96.7944 | 0 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 2.9489 | 16.7944
2026-01-05 | Mon | Drilling | 16 | 16 | 712 | 960 | 660.7876 | 660.7876 | 580.7876 | 38.7192 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.2689 | 3.7311 |  | 0 | 41 |  | 0 | 98.4646 | 1.6702 | 18.4646 |  | 0 |  | -660.7876 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.7311 | 2.2808 | 18.4646
2026-01-06 | Tue | Drilling | 16 | 16 | 728 | 960 | 670.7248 | 670.7248 | 590.7248 | 39.3817 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.5896 | 3.4104 | 2 | 0 | 44 | 3 | 0 | 100.1208 | 1.6562 | 0.1208 | 20 | 0 |  | -670.7248 | #N/A | -720 | -624 | -688 | #N/A | -72 | #N/A | -144 | #N/A | -216 | #N/A | 3.4104 | 4.6183 | 0.1208
2026-01-07 | Wed | Drilling | 16 | 16 | 744 | 960 | 680.5804 | 680.5804 | 600.5804 | 40.0387 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.9102 | 5.0898 |  | 0 | 44 |  | 0 | 101.7634 | 1.6426 | 1.7634 |  | 0 |  | -680.5804 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0898 | 3.9613 | 1.7634
2026-01-08 | Thu | Drilling | 16 | 16 | 760 | 960 | 690.3562 | 690.3562 | 610.3562 | 40.6904 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.2309 | 4.7691 |  | 0 | 44 |  | 0 | 103.3927 | 1.6293 | 3.3927 |  | 0 |  | -690.3562 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.7691 | 3.3096 | 3.3927
2026-01-09 | Fri | Drilling | 16 | 16 | 776 | 960 | 700.0543 | 700.0543 | 620.0543 | 41.337 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.5515 | 4.4485 |  | 0 | 44 |  | 0 | 105.0091 | 1.6163 | 5.0091 |  | 0 |  | -700.0543 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4485 | 2.663 | 5.0091
2026-01-10 | Sat | Drilling | 16 | 16 | 792 | 960 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.8722 | 4.1278 |  | 0 | 44 |  | 0 | 106.6127 | 1.6037 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.1278 | 2.0216 | 6.6127
2026-01-11 | Sun | REST | 0 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 15.8722 | 4.1278 |  | 0 | 44 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.1278 | 2.0216 | 6.6127
2026-01-12 | Mon | Drilling | 16 | 16 | 808 | 960 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 16.1928 | 3.8072 |  | 0 | 44 |  | 0 | 108.2041 | 1.5913 | 8.2041 |  | 0 |  | -719.2244 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.8072 | 1.385 | 8.2041
2026-01-13 | Tue | Drilling | 16 | 16 | 824 | 960 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0.32065 | 16.5135 | 3.4865 |  | 0 | 44 |  | 0 | 109.7833 | 1.5792 | -0.016699 | 9.8 | 0 |  | -728.6998 | -80 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | #N/A | 3.4865 | 0.75335 | -0.016699
2026-01-14 | Wed | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 24 | 1440 | 259.4033 | 10.7642 | 10.7642 | 259.4033 | 0.58537 | 17.0989 | 2.9011 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -259.4033 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.9011 | 11.5175 | -0.016699
2026-01-15 | Thu | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 48 | 1440 | 400.4713 | 19.2283 | 8.4641 | 400.4713 | 0.58537 | 17.6842 | 2.3158 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3158 | 19.9816 | -0.016699
2026-01-16 | Fri | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 72 | 1440 | 510.1938 | 25.8116 | 6.5834 | 510.1938 | 0.58537 | 18.2696 | 1.7304 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -510.1938 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.7304 | 26.565 | -0.016699
2026-01-17 | Sat | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 96 | 1440 | 603.2085 | 31.3925 | 5.5809 | 603.2085 | 0.58537 | 18.855 | 1.145 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.145 | 32.1459 | -0.016699
2026-01-18 | Sun | Bailing | 24 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 24 | 120 | 1440 | 685.4061 | 36.3244 | 4.9319 | 685.4061 | 0.58537 | 19.4403 | 0.55967 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -685.4061 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.55967 | 37.0777 | -0.016699
2026-01-19 | Mon | Bailing | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 12 | 132 | 720 | 723.4668 | 38.608 | 2.2836 | 723.4668 | 0.29268 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | -0.016699
2026-01-20 | Tue | Drill & Tent Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | -0.016699
2026-01-21 | Wed | Drill & Tent Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | -0.016699
2026-01-22 | Thu | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | -0.016699
2026-01-23 | Fri | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | -0.016699
2026-01-24 | Sat | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | -0.016699
2026-01-25 | Sun | Camp Teardown | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | -0.016699
2026-01-26 | Mon | Camp Closed | 12 | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | -0.016699 |  | -0.016699 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 0.26699 | 39.3614 | -0.016699
2026-01-27 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-01-28 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-01-29 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-01-30 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-01-31 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-01 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-02 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-03 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-04 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-05 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-06 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-07 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-08 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-09 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-10 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-11 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-12 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-13 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-14 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-15 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-16 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-17 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-18 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-19 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-20 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-21 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-22 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-23 | Mon |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-24 | Tue |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-25 | Wed |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-26 | Thu |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-27 | Fri |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-02-28 | Sat |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
2026-03-01 | Sun |  |  | 0 | 824 | 0 | 728.6998 | 728.6998 | 648.6998 | 43.2467 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.733 | 0.26699 |  | 0 | 44 |  | 0 | 109.7833 | 0 | 0 |  | 0 |  | -728.6998 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.26699 | 39.3614 | 0
Formulas:
Date = [Date, row above]+1

## 04-07-25-Scen5-WorstCargoJIT
Date | Day | Drilling Critical Path | Working Day (hrs) | Drilling Day (hrs) | Cumulative Drilling Time (hrs) | Drilling Day (mins) | New Drilling Depth (m) | End of Day Drill Depth (m) | Drill Fluid Height (m) | Drill Fluid Used (Drums) | Bailing Day (hrs) | Cumulative Bailing Time (hrs) | Bailing Day (mins) | New Bailing Depth (m) | Cumulative Drill Fluid Recovered (Drums) | Daily Drill Fluid Recovered (Drums) | End of Day Bailing Depth (m) | Drilling/Bailing Fuel Burn (Drums) | Cumulative Drilling/Bailing Fuel Burn (Drums) | Drilling/Bailing Fuel in Field (Drums) | Drilling/Bailing Fuel Planned Arrival (Drums) | Fuel Still Required for Drilling/Bailing IN (Drums) | Drill Fluid in Field (Drums) | Drill Fluid Planned Arrival (Drums) | Drill Fluid Still Required IN (Drums) | Ice Core Boxes Filled | Today's Ice Core Boxes Filled | Filled Ice Core Boxes in Field | Ice Core Boxes Planned Removal | Ice Core Box Flight Ready OUT | Input | End of Day Drill Depth | End of Day Bailing Depth | Bedrock | 10,000YBP Min | 10,000YBP Max | Able to Output | Drilling Fuel Planned | Drilling Fuel Still Needed | Drill Fluid Planned In | Drill Fluid Still Needed In | Ice Core Boxes Planned OUT | Ice Core Boxes Still Needed OUT | Drilling Fuel in Camp | D60 in Camp (excl Borehole) | Filled Core Boxes in Camp | Scenario 5: IMPOSSIBLE SEASON: Unrealistic Perfect Setup & Put In, 24hr Drilling. No Issues. Extreme Case only for considering worst-case JIT cargo requirements. | [6 empty] | How to use this Scenario Planner:
2025-11-12 | Wed | Open Camp | 12 | 0 | 0 | 0 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 | 0 | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 |  | Date | PAX |  |  | Date | PAX | This is an input cell |  | input | do not change values in any cell but these
2025-11-13 | Thu | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | First Input | 2025-11-12 | 5 |  | First Output | 2026-01-21 | 5 | Do not cut and paste cells as it will break the formulae that make this sheet work (you can copy though)
2025-11-14 | Fri | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | Second Input | 2025-11-17 | 5 |  | Second Output | 2026-02-02 | 5
2025-11-15 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 1. Set the input and output dates (found above the charts)
2025-11-16 | Sun | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 2. Set drill, project, and logistics constraints in the "Drilling Spec" sheet.
2025-11-17 | Mon | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 3. Fill in the "Drilling Critical Path" and "Working Day (hrs)" columns with the activities that will be undertaken each day. There are special values you can put in "Drilling Critical Path" that will help - you must type them in without typos!
2025-11-18 | Tue | REST | 0 | 0 | 0 | 0 | #VALUE! | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 4 |  | 0 | 0 | 0 | 0 |  | 0 |  | -70 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-19 | Wed | Drilling | 8 | 8 | 8 | 480 | 79.8333 | 79.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.16033 | 5.8397 |  | 0 | 4 |  | 0 | 1.6389 | 1.6389 | 1.6389 |  | 0 |  | -79.8333 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.8397 | 4 | 1.6389
2025-11-20 | Thu | Drilling | 8 | 8 | 16 | 480 | 89.5102 | 89.5102 | 9.5102 | 0.63401 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.32065 | 5.6793 |  | 0 | 4 |  | 0 | 3.2517 | 1.6128 | 3.2517 |  | 0 |  | -89.5102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6793 | 3.366 | 3.2517 | [8 empty] | REST |  | counts as a rest day.
2025-11-21 | Fri | Drilling | 8 | 8 | 24 | 480 | 99.0379 | 99.0379 | 19.0379 | 1.2692 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.48098 | 5.519 |  | 0 | 4 |  | 0 | 4.8397 | 1.5879 | 4.8397 |  | 0 |  | -99.0379 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.519 | 2.7308 | 4.8397 | [8 empty] | Drilling |  | counts the hours towards drilling progress.
2025-11-22 | Sat | Drilling | 24 | 24 | 48 | 1440 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 0.96195 | 5.038 |  | 0 | 4 |  | 0 | 9.4651 | 4.6254 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.038 | 0.88064 | 9.4651 | [8 empty] | Bailing |  | counts the hours towards bailing progress.
2025-11-23 | Sun | REST | 0 | 0 | 48 | 0 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.96195 | 5.038 |  | 0 | 4 |  | 6 | 9.4651 | 0 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.038 | 0.88064 | 9.4651 | [8 empty] | Camp Closed |  | notes when we're finished in camp.
2025-11-24 | Mon | Drilling | 24 | 24 | 72 | 1440 | 153.4144 | 153.4144 | 73.4144 | 4.8943 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.4429 | 4.5571 |  | 0 | 10 |  | 0 | 13.9024 | 4.4373 | 13.9024 |  | 0 |  | -153.4144 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5571 | 5.1057 | 13.9024 | [8 empty] | The upper graph will show drilling and bailing progress given your inputted activities, ensure you reach target depth/bedrock!
2025-11-25 | Tue | Drilling | 24 | 24 | 96 | 1440 | 179.0374 | 179.0374 | 99.0374 | 6.6025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.9239 | 4.0761 |  | 0 | 10 |  | 0 | 18.1729 | 4.2705 | 18.1729 |  | 0 |  | -179.0374 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0761 | 3.3975 | 18.1729
2025-11-26 | Wed | Drilling | 24 | 24 | 120 | 1440 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.4049 | 3.5951 |  | 0 | 10 |  | 0 | 22.2941 | 4.1212 | 22.2941 |  | 20 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 3.5951 | 1.749 | 22.2941 | [8 empty] | Note: You need to consider yourself whether the inputted activities are realistic given the staffing available.
2025-11-27 | Thu | Drilling | 24 | 24 | 144 | 1440 | 227.6833 | 227.6833 | 147.6833 | 9.8456 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.8859 | 3.1141 |  | 0 | 10 |  | 6 | 26.2805 | 3.9865 | 6.2805 |  | 0 |  | -227.6833 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 3.1141 | 0.15445 | 6.2805
2025-11-28 | Fri | Drilling | 24 | 24 | 168 | 1440 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.3668 | 2.6332 |  | 0 | 16 |  | 0 | 30.1447 | 3.8642 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.6332 | 4.6088 | 10.1447 | [8 empty] | The graph also will show crosses on the dates where logistic input is required to keep the planned schedule moving. For fuel and drilling fluid, crosses mark the last chance to get more in before drilling ops shut down. For ice core boxes crosses mark the earliest a full load of boxes would be ready for removal.
2025-11-29 | Sat | Drilling | 24 | 24 | 192 | 1440 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.8478 | 2.1522 |  | 0 | 16 |  | 0 | 33.8973 | 3.7525 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1522 | 3.1078 | 13.8973
2025-11-30 | Sun | REST | 0 | 0 | 192 | 0 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.8478 | 2.1522 |  | 0 | 16 |  | 0 | 33.8973 | 0 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1522 | 3.1078 | 13.8973
2025-12-01 | Mon | Drilling | 24 | 24 | 216 | 1440 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.3288 | 1.6712 |  | 0 | 16 |  | 0 | 37.5473 | 3.65 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6712 | 1.6478 | 17.5473
2025-12-02 | Tue | Drilling | 24 | 24 | 240 | 1440 | 316.6164 | 316.6164 | 236.6164 | 15.7744 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.8098 | 1.1902 |  | 0 | 16 |  | 6 | 41.1027 | 3.5555 | 21.1027 |  | 20 |  | -316.6164 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | -216 | 1.1902 | 0.22557 | 21.1027
2025-12-03 | Wed | Drilling | 24 | 24 | 264 | 1440 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.2907 | 0.70927 |  | 0 | 22 |  | 0 | 44.5706 | 3.4679 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.70927 | 4.8384 | 4.5706 | [8 empty] | Note: Drilling/Bailing fuel only counts what is needed for drilling ops, fuel for other camp activities should be considered separately.
2025-12-04 | Thu | Drilling | 24 | 24 | 288 | 1440 | 357.7428 | 357.7428 | 277.7428 | 18.5162 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.7717 | 0.22829 |  | 6 | 22 |  | 0 | 47.9571 | 3.3865 | 7.9571 |  | 0 |  | -357.7428 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.22829 | 3.4838 | 7.9571
2025-12-05 | Fri | Drilling | 24 | 24 | 312 | 1440 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.2527 | 5.7473 |  | 0 | 22 |  | 0 | 51.2677 | 3.3106 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7473 | 2.1596 | 11.2677 | [7 empty] | 4. Schedule deliveries of fuel and drill fluid, and pickup of ice core boxes. Use the "Drilling/Bailing Fuel Planned Arrival (Drums)", " Drill Fluid Planned Arrival (Drums)", and "Ice Core Boxes Planned Removal" columns for this. These will be marked on the graph as circles, and the cross showing needs that remain unscheduled will update automatically.
2025-12-06 | Sat | Drilling | 24 | 24 | 336 | 1440 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.7337 | 5.2663 |  | 0 | 22 |  | 0 | 54.5073 | 3.2396 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.2663 | 0.86376 | 14.5073
2025-12-07 | Sun | REST | 0 | 0 | 336 | 0 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.7337 | 5.2663 |  | 0 | 22 |  | 6 | 54.5073 | 2.1316e-14 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.2663 | 0.86376 | 14.5073
2025-12-08 | Mon | Drilling | 24 | 24 | 360 | 1440 | 416.0811 | 416.0811 | 336.0811 | 22.4054 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.2146 | 4.7854 |  | 0 | 28 |  | 0 | 57.6802 | 3.1729 | 17.6802 |  | 0 |  | -416.0811 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.7854 | 5.5946 | 17.6802
2025-12-09 | Tue | Drilling | 24 | 24 | 384 | 1440 | 434.7424 | 434.7424 | 354.7424 | 23.6495 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.6956 | 4.3044 |  | 0 | 28 |  | 0 | 60.7904 | 3.1102 | 20.7904 |  | 20 |  | -434.7424 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.3044 | 4.3505 | 20.7904
2025-12-10 | Wed | Drilling | 24 | 24 | 408 | 1440 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.1766 | 3.8234 |  | 0 | 28 |  | 0 | 63.8415 | 3.0511 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.8234 | 3.1301 | 3.8415 | [8 empty] | The totals of these 'consumables' in camp are shown in the lower graph. (Note drilling fluid in the borehole is excluded).
2025-12-11 | Thu | Drilling | 24 | 24 | 432 | 1440 | 471.0203 | 471.0203 | 391.0203 | 26.068 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.6576 | 3.3424 |  | 0 | 28 |  | 0 | 66.8367 | 2.9952 | 6.8367 |  | 0 |  | -471.0203 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3424 | 1.932 | 6.8367
2025-12-12 | Fri | Drilling | 24 | 24 | 456 | 1440 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.1385 | 2.8615 |  | 0 | 28 |  | 6 | 69.779 | 2.9423 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 2.8615 | 0.75505 | 9.779 | [8 empty] | Note: Check the "Filled Ice Core Boxes in Field" column to avoid scheduling removing more core boxes than you have ready!
2025-12-13 | Sat | Drilling | 24 | 24 | 480 | 1440 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.6195 | 2.3805 |  | 0 | 34 |  | 0 | 72.6712 | 2.8921 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3805 | 5.5982 | 12.6712
2025-12-14 | Sun | REST | 0 | 0 | 480 | 0 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9.6195 | 2.3805 |  | 0 | 34 |  | 0 | 72.6712 | 0 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3805 | 5.5982 | 12.6712 | [7 empty] | 5. Assess feasibility of the planned season (logistic demands realistic, enough PAX in field, enough time for issues and bad weather, rest periods in long seasons, room for other non-drilling activities, etc)
2025-12-15 | Mon | Drilling | 24 | 24 | 504 | 1440 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.1005 | 1.8995 |  | 0 | 34 |  | 0 | 75.5156 | 2.8444 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8995 | 4.4604 | 15.5156
2025-12-16 | Tue | Drilling | 24 | 24 | 528 | 1440 | 539.8871 | 539.8871 | 459.8871 | 30.6591 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.5815 | 1.4185 |  | 0 | 34 |  | 0 | 78.3145 | 2.799 | 18.3145 |  | 0 |  | -539.8871 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4185 | 3.3409 | 18.3145
2025-12-17 | Wed | Drilling | 24 | 24 | 552 | 1440 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.0624 | 0.93756 |  | 0 | 34 |  | 0 | 81.0702 | 2.7557 | 21.0702 |  | 20 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 0.93756 | 2.2386 | 21.0702 | [7 empty] | 6. Assess getting everything out again after! There'll be a lot of recovered drill fluid in drums…
2025-12-18 | Thu | Drilling | 24 | 24 | 576 | 1440 | 572.7068 | 572.7068 | 492.7068 | 32.8471 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.5434 | 0.45659 |  | 6 | 34 |  | 0 | 83.7845 | 2.7143 | 3.7845 |  | 0 |  | -572.7068 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.45659 | 1.1529 | 3.7845
2025-12-19 | Fri | Drilling | 24 | 24 | 600 | 1440 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.0244 | 5.9756 |  | 0 | 34 |  | 6 | 86.4592 | 2.6747 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.9756 | 0.082991 | 6.4592
2025-12-20 | Sat | Drilling | 24 | 24 | 624 | 1440 | 604.5762 | 604.5762 | 524.5762 | 34.9717 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.5054 | 5.4946 |  | 0 | 40 |  | 0 | 89.096 | 2.6368 | 9.096 |  | 0 |  | -604.5762 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.4946 | 5.0283 | 9.096
2025-12-21 | Sun | REST | 0 | 0 | 624 | 0 | 604.5762 | 604.5762 | 524.5762 | 34.9717 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.5054 | 5.4946 |  | 0 | 40 |  | 0 | 89.096 | 0 | 9.096 |  | 0 |  | -604.5762 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.4946 | 5.0283 | 9.096
2025-12-22 | Mon | Drilling | 24 | 24 | 648 | 1440 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.9863 | 5.0137 |  | 0 | 40 |  | 0 | 91.6966 | 2.6005 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 3.988 | 11.6966
2025-12-23 | Tue | Drilling | 24 | 24 | 672 | 1440 | 635.5735 | 635.5735 | 555.5735 | 37.0382 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 13.4673 | 4.5327 |  | 0 | 40 |  | 0 | 94.2623 | 2.5657 | 14.2623 |  | 0 |  | -635.5735 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5327 | 2.9618 | 14.2623
2025-12-24 | Wed | Drilling | 24 | 24 | 696 | 1440 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 13.9483 | 4.0517 |  | 0 | 40 |  | 0 | 96.7944 | 2.5322 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 1.9489 | 16.7944
2025-12-25 | Thu | REST | 0 | 0 | 696 | 0 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13.9483 | 4.0517 |  | 0 | 40 |  | 0 | 96.7944 | 0 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 1.9489 | 16.7944 | TOTAL DRILLING | 35 | days | 792 | hrs
2025-12-26 | Fri | Drilling | 24 | 24 | 720 | 1440 | 665.7666 | 665.7666 | 585.7666 | 39.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 14.4293 | 3.5707 |  | 0 | 40 |  | 6 | 99.2944 | 2.5 | 19.2944 |  | 0 |  | -665.7666 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 3.5707 | 0.9489 | 19.2944 | TOTAL BAILING | 6 | days | 132 | hrs
2025-12-27 | Sat | Drilling | 24 | 24 | 744 | 1440 | 680.5804 | 680.5804 | 600.5804 | 40.0387 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 14.9102 | 3.0898 |  | 0 | 46 |  | 0 | 101.7634 | 2.469 | 21.7634 |  | 20 |  | -680.5804 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 3.0898 | 5.9613 | 21.7634
2025-12-28 | Sun | Drilling | 24 | 24 | 768 | 1440 | 695.2149 | 695.2149 | 615.2149 | 41.0143 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 15.3912 | 2.6088 |  | 0 | 46 |  | 0 | 104.2025 | 2.4391 | 4.2025 |  | 0 |  | -695.2149 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.6088 | 4.9857 | 4.2025 | TOTAL WORKING | 51 | days | 1056 | hrs
2025-12-29 | Mon | Drilling | 24 | 24 | 792 | 1440 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0.48098 | 15.8722 | 2.1278 |  | 0 | 46 |  | 0 | 106.6127 | 2.4103 | 6.6127 |  | 0 |  | -709.6765 | -80 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1278 | 4.0216 | 6.6127 | TOTAL REST | 9 | days
2025-12-30 | Tue | Bailing | 24 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 24 | 24 | 1440 | 259.4033 | 10.7642 | 10.7642 | 259.4033 | 0.58537 | 16.4576 | 1.5424 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -259.4033 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.5424 | 14.7858 | 6.6127
2025-12-31 | Wed | REST | 0 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 24 | 0 | 259.4033 | 10.7642 | 0 | 259.4033 | 0 | 16.4576 | 1.5424 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -259.4033 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.5424 | 14.7858 | 6.6127 | FIELD TIME | 60 | days
2026-01-01 | Thu | Bailing | 24 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 24 | 48 | 1440 | 400.4713 | 19.2283 | 8.4641 | 400.4713 | 0.58537 | 17.0429 | 0.95707 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.95707 | 23.2498 | 6.6127 | SLACK | 22 | days
2026-01-02 | Fri | Bailing | 24 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 24 | 72 | 1440 | 510.1938 | 25.8116 | 6.5834 | 510.1938 | 0.58537 | 17.6283 | 0.37171 |  | 6 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -510.1938 | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.37171 | 29.8332 | 6.6127
2026-01-03 | Sat | Bailing | 24 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 24 | 96 | 1440 | 603.2085 | 31.3925 | 5.5809 | 603.2085 | 0.58537 | 18.2137 | 5.7863 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7863 | 35.4141 | 6.6127
2026-01-04 | Sun | REST | 0 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 96 | 0 | 603.2085 | 31.3925 | 0 | 603.2085 | 0 | 18.2137 | 5.7863 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7863 | 35.4141 | 6.6127
2026-01-05 | Mon | Bailing | 24 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 24 | 120 | 1440 | 685.4061 | 36.3244 | 4.9319 | 685.4061 | 0.58537 | 18.799 | 5.201 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -685.4061 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.201 | 40.3459 | 6.6127
2026-01-06 | Tue | Bailing | 12 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 12 | 132 | 720 | 723.4668 | 38.608 | 2.2836 | 723.4668 | 0.29268 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 6.6127
2026-01-07 | Wed | Drill & Tent Teardown | 12 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 6.6127
2026-01-08 | Thu | Drill & Tent Teardown | 12 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 6.6127
2026-01-09 | Fri | Camp Teardown | 12 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 6.6127
2026-01-10 | Sat | Camp Teardown | 12 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 6.6127
2026-01-11 | Sun | Camp Closed | 12 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 6.6127 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.9083 | 42.6296 | 6.6127
2026-01-12 | Mon |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-13 | Tue |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-14 | Wed |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-15 | Thu |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-16 | Fri |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-17 | Sat |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-18 | Sun |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-19 | Mon |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-20 | Tue |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-21 | Wed |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-22 | Thu |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-23 | Fri |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-24 | Sat |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-25 | Sun |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-26 | Mon |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-27 | Tue |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-28 | Wed |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-29 | Thu |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-30 | Fri |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-01-31 | Sat |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-01 | Sun |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-02 | Mon |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-03 | Tue |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-04 | Wed |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-05 | Thu |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-06 | Fri |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-07 | Sat |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-08 | Sun |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-09 | Mon |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-10 | Tue |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-11 | Wed |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-12 | Thu |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-13 | Fri |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-14 | Sat |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-15 | Sun |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-16 | Mon |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-17 | Tue |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-18 | Wed |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-19 | Thu |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-20 | Fri |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-21 | Sat |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-22 | Sun |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-23 | Mon |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-24 | Tue |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-25 | Wed |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-26 | Thu |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-27 | Fri |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-02-28 | Sat |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
2026-03-01 | Sun |  |  | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.0917 | 4.9083 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 0 |  | 0 |  | -709.6765 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.9083 | 42.6296 | 0
Formulas:
Date = [Date, row above]+1

## 04-07-25-Scen6-Good,16hr
Date | Day | Drilling Critical Path | Working Day (hrs) | Drilling Day (hrs) | Cumulative Drilling Time (hrs) | Drilling Day (mins) | New Drilling Depth (m) | End of Day Drill Depth (m) | Drill Fluid Height (m) | Drill Fluid Used (Drums) | Bailing Day (hrs) | Cumulative Bailing Time (hrs) | Bailing Day (mins) | New Bailing Depth (m) | Cumulative Drill Fluid Recovered (Drums) | Daily Drill Fluid Recovered (Drums) | End of Day Bailing Depth (m) | Drilling/Bailing Fuel Burn (Drums) | Cumulative Drilling/Bailing Fuel Burn (Drums) | Drilling/Bailing Fuel in Field (Drums) | Drilling/Bailing Fuel Planned Arrival (Drums) | Fuel Still Required for Drilling/Bailing IN (Drums) | Drill Fluid in Field (Drums) | Drill Fluid Planned Arrival (Drums) | Drill Fluid Still Required IN (Drums) | Ice Core Boxes Filled | Today's Ice Core Boxes Filled | Filled Ice Core Boxes in Field | Ice Core Boxes Planned Removal | Ice Core Box Flight Ready OUT | Input | End of Day Drill Depth | End of Day Bailing Depth | Bedrock | 10,000YBP Min | 10,000YBP Max | Able to Output | Drilling Fuel Planned | Drilling Fuel Still Needed | Drill Fluid Planned In | Drill Fluid Still Needed In | Ice Core Boxes Planned OUT | Ice Core Boxes Still Needed OUT | Drilling Fuel in Camp | D60 in Camp (excl Borehole) | Filled Core Boxes in Camp | Scenario 6: Can we avoid 24hr drilling? NO! | [6 empty] | How to use this Scenario Planner:
2025-11-12 | Wed | Open Camp | 12 | 0 | 0 | 0 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 | 0 | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 |  | Date | PAX |  |  | Date | PAX | This is an input cell |  | input | do not change values in any cell but these
2025-11-13 | Thu | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | First Input | 2025-11-12 | 5 |  | First Output | 2026-01-21 | 5 | Do not cut and paste cells as it will break the formulae that make this sheet work (you can copy though)
2025-11-14 | Fri | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | Second Input | 2025-11-17 | 5 |  | Second Output | 2026-02-02 | 5
2025-11-15 | Sat | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 1. Set the input and output dates (found above the charts)
2025-11-16 | Sun | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 2. Set drill, project, and logistics constraints in the "Drilling Spec" sheet.
2025-11-17 | Mon | REST | 0 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 3. Fill in the "Drilling Critical Path" and "Working Day (hrs)" columns with the activities that will be undertaken each day. There are special values you can put in "Drilling Critical Path" that will help - you must type them in without typos!
2025-11-18 | Tue | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-19 | Wed | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-20 | Thu | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | REST |  | counts as a rest day.
2025-11-21 | Fri | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Drilling |  | counts the hours towards drilling progress.
2025-11-22 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Bailing |  | counts the hours towards bailing progress.
2025-11-23 | Sun | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Camp Closed |  | notes when we're finished in camp.
2025-11-24 | Mon | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | The upper graph will show drilling and bailing progress given your inputted activities, ensure you reach target depth/bedrock!
2025-11-25 | Tue | REST | 0 | 0 | 0 | 0 | #VALUE! | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 4 |  | 0 | 0 | 0 | 0 |  | 0 |  | -70 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-26 | Wed | Drilling | 8 | 8 | 8 | 480 | 79.8333 | 79.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.16033 | 5.8397 |  | 0 | 4 |  | 0 | 1.6389 | 1.6389 | 1.6389 |  | 0 |  | -79.8333 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.8397 | 4 | 1.6389 | [8 empty] | Note: You need to consider yourself whether the inputted activities are realistic given the staffing available.
2025-11-27 | Thu | Drilling | 8 | 8 | 16 | 480 | 89.5102 | 89.5102 | 9.5102 | 0.63401 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.32065 | 5.6793 |  | 0 | 4 |  | 0 | 3.2517 | 1.6128 | 3.2517 |  | 0 |  | -89.5102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6793 | 3.366 | 3.2517
2025-11-28 | Fri | Drilling | 8 | 8 | 24 | 480 | 99.0379 | 99.0379 | 19.0379 | 1.2692 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.48098 | 5.519 |  | 0 | 4 |  | 0 | 4.8397 | 1.5879 | 4.8397 |  | 0 |  | -99.0379 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.519 | 2.7308 | 4.8397 | [8 empty] | The graph also will show crosses on the dates where logistic input is required to keep the planned schedule moving. For fuel and drilling fluid, crosses mark the last chance to get more in before drilling ops shut down. For ice core boxes crosses mark the earliest a full load of boxes would be ready for removal.
2025-11-29 | Sat | Drilling | 16 | 16 | 40 | 960 | 117.672 | 117.672 | 37.672 | 2.5115 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 0.80163 | 5.1984 |  | 0 | 4 |  | 0 | 7.9453 | 3.1057 | 7.9453 |  | 0 |  | -117.672 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.1984 | 1.4885 | 7.9453
2025-11-30 | Sun | REST | 0 | 0 | 40 | 0 | 117.672 | 117.672 | 37.672 | 2.5115 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.80163 | 5.1984 |  | 0 | 4 |  | 0 | 7.9453 | 0 | 7.9453 |  | 0 |  | -117.672 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.1984 | 1.4885 | 7.9453
2025-12-01 | Mon | Drilling | 16 | 16 | 56 | 960 | 135.7837 | 135.7837 | 55.7837 | 3.7189 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 1.1223 | 4.8777 |  | 0 | 4 |  | 6 | 10.9639 | 3.0186 | 10.9639 |  | 0 |  | -135.7837 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 4.8777 | 0.28109 | 10.9639
2025-12-02 | Tue | Drilling | 16 | 16 | 72 | 960 | 153.4144 | 153.4144 | 73.4144 | 4.8943 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 1.4429 | 4.5571 |  | 0 | 10 |  | 0 | 13.9024 | 2.9385 | 13.9024 |  | 0 |  | -153.4144 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5571 | 5.1057 | 13.9024
2025-12-03 | Wed | Drilling | 16 | 16 | 88 | 960 | 170.6008 | 170.6008 | 90.6008 | 6.0401 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 1.7636 | 4.2364 |  | 0 | 10 |  | 0 | 16.7668 | 2.8644 | 16.7668 |  | 0 |  | -170.6008 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.2364 | 3.9599 | 16.7668 | [8 empty] | Note: Drilling/Bailing fuel only counts what is needed for drilling ops, fuel for other camp activities should be considered separately.
2025-12-04 | Thu | Drilling | 16 | 16 | 104 | 960 | 187.3746 | 187.3746 | 107.3746 | 7.1583 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 2.0842 | 3.9158 |  | 0 | 10 |  | 0 | 19.5624 | 2.7956 | 19.5624 |  | 0 |  | -187.3746 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.9158 | 2.8417 | 19.5624
2025-12-05 | Fri | Drilling | 16 | 16 | 120 | 960 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 2.4049 | 3.5951 |  | 0 | 10 |  | 0 | 22.2941 | 2.7316 | 22.2941 |  | 20 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 3.5951 | 1.749 | 22.2941 | [7 empty] | 4. Schedule deliveries of fuel and drill fluid, and pickup of ice core boxes. Use the "Drilling/Bailing Fuel Planned Arrival (Drums)", " Drill Fluid Planned Arrival (Drums)", and "Ice Core Boxes Planned Removal" columns for this. These will be marked on the graph as circles, and the cross showing needs that remain unscheduled will update automatically.
2025-12-06 | Sat | Drilling | 16 | 16 | 136 | 960 | 219.7952 | 219.7952 | 139.7952 | 9.3197 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 2.7255 | 3.2745 |  | 0 | 10 |  | 0 | 24.9659 | 2.6718 | 4.9659 |  | 0 |  | -219.7952 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.2745 | 0.68032 | 4.9659
2025-12-07 | Sun | REST | 0 | 0 | 136 | 0 | 219.7952 | 219.7952 | 139.7952 | 9.3197 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.7255 | 3.2745 |  | 0 | 10 |  | 6 | 24.9659 | 0 | 4.9659 |  | 0 |  | -219.7952 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 3.2745 | 0.68032 | 4.9659
2025-12-08 | Mon | Drilling | 16 | 16 | 152 | 960 | 235.4898 | 235.4898 | 155.4898 | 10.366 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 3.0462 | 2.9538 |  | 0 | 16 |  | 0 | 27.5816 | 2.6158 | 7.5816 |  | 0 |  | -235.4898 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.9538 | 5.634 | 7.5816
2025-12-09 | Tue | Drilling | 16 | 16 | 168 | 960 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 3.3668 | 2.6332 |  | 0 | 16 |  | 0 | 30.1447 | 2.5631 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.6332 | 4.6088 | 10.1447
2025-12-10 | Wed | Drilling | 16 | 16 | 184 | 960 | 265.9494 | 265.9494 | 185.9494 | 12.3966 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 3.6875 | 2.3125 |  | 0 | 16 |  | 0 | 32.6582 | 2.5135 | 12.6582 |  | 0 |  | -265.9494 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3125 | 3.6034 | 12.6582 | [8 empty] | The totals of these 'consumables' in camp are shown in the lower graph. (Note drilling fluid in the borehole is excluded).
2025-12-11 | Thu | Drilling | 16 | 16 | 200 | 960 | 280.7495 | 280.7495 | 200.7495 | 13.3833 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 4.0081 | 1.9919 |  | 0 | 16 |  | 0 | 35.1249 | 2.4667 | 15.1249 |  | 0 |  | -280.7495 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.9919 | 2.6167 | 15.1249
2025-12-12 | Fri | Drilling | 16 | 16 | 216 | 960 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 4.3288 | 1.6712 |  | 0 | 16 |  | 0 | 37.5473 | 2.4224 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6712 | 1.6478 | 17.5473 | [8 empty] | Note: Check the "Filled Ice Core Boxes in Field" column to avoid scheduling removing more core boxes than you have ready!
2025-12-13 | Sat | Drilling | 16 | 16 | 232 | 960 | 309.5658 | 309.5658 | 229.5658 | 15.3044 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 4.6494 | 1.3506 |  | 0 | 16 |  | 0 | 39.9276 | 2.3804 | 19.9276 |  | 0 |  | -309.5658 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.3506 | 0.69561 | 19.9276
2025-12-14 | Sun | REST | 0 | 0 | 232 | 0 | 309.5658 | 309.5658 | 229.5658 | 15.3044 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4.6494 | 1.3506 |  | 0 | 16 |  | 6 | 39.9276 | 0 | 19.9276 |  | 0 |  | -309.5658 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 1.3506 | 0.69561 | 19.9276 | [7 empty] | 5. Assess feasibility of the planned season (logistic demands realistic, enough PAX in field, enough time for issues and bad weather, rest periods in long seasons, room for other non-drilling activities, etc)
2025-12-15 | Mon | Drilling | 16 | 16 | 248 | 960 | 323.6086 | 323.6086 | 243.6086 | 16.2406 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 4.9701 | 1.0299 |  | 0 | 22 |  | 0 | 42.2681 | 2.3405 | 22.2681 |  | 20 |  | -323.6086 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 1.0299 | 5.7594 | 22.2681
2025-12-16 | Tue | Drilling | 16 | 16 | 264 | 960 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 5.2907 | 0.70927 |  | 0 | 22 |  | 0 | 44.5706 | 2.3025 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.70927 | 4.8384 | 4.5706
2025-12-17 | Wed | Drilling | 16 | 16 | 280 | 960 | 351.0219 | 351.0219 | 271.0219 | 18.0681 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 5.6114 | 0.38862 |  | 0 | 22 |  | 0 | 46.837 | 2.2664 | 6.837 |  | 0 |  | -351.0219 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.38862 | 3.9319 | 6.837 | [7 empty] | 6. Assess getting everything out again after! There'll be a lot of recovered drill fluid in drums…
2025-12-18 | Thu | Drilling | 16 | 16 | 296 | 960 | 364.4131 | 364.4131 | 284.4131 | 18.9609 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 5.932 | 0.067967 |  | 6 | 22 |  | 0 | 49.0688 | 2.2319 | 9.0688 |  | 0 |  | -364.4131 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.067967 | 3.0391 | 9.0688
2025-12-19 | Fri | Drilling | 16 | 16 | 312 | 960 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 6.2527 | 5.7473 |  | 0 | 22 |  | 0 | 51.2677 | 2.1989 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7473 | 2.1596 | 11.2677
2025-12-20 | Sat | Drilling | 16 | 16 | 328 | 960 | 390.6102 | 390.6102 | 310.6102 | 20.7073 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 6.5733 | 5.4267 |  | 0 | 22 |  | 0 | 53.435 | 2.1673 | 13.435 |  | 0 |  | -390.6102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.4267 | 1.2927 | 13.435
2025-12-21 | Sun | REST | 0 | 0 | 328 | 0 | 390.6102 | 390.6102 | 310.6102 | 20.7073 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.5733 | 5.4267 |  | 0 | 22 |  | 0 | 53.435 | 0 | 13.435 |  | 0 |  | -390.6102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.4267 | 1.2927 | 13.435
2025-12-22 | Mon | Drilling | 16 | 16 | 344 | 960 | 403.4326 | 403.4326 | 323.4326 | 21.5622 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 6.894 | 5.106 |  | 0 | 22 |  | 6 | 55.5721 | 2.1371 | 15.5721 |  | 0 |  | -403.4326 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.106 | 0.43782 | 15.5721
2025-12-23 | Tue | Drilling | 16 | 16 | 360 | 960 | 416.0811 | 416.0811 | 336.0811 | 22.4054 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 7.2146 | 4.7854 |  | 0 | 28 |  | 0 | 57.6802 | 2.1081 | 17.6802 |  | 0 |  | -416.0811 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.7854 | 5.5946 | 17.6802
2025-12-24 | Wed | Drilling | 16 | 16 | 376 | 960 | 428.5624 | 428.5624 | 348.5624 | 23.2375 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 7.5353 | 4.4647 |  | 0 | 28 |  | 0 | 59.7604 | 2.0802 | 19.7604 |  | 0 |  | -428.5624 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4647 | 4.7625 | 19.7604
2025-12-25 | Thu | REST | 0 | 0 | 376 | 0 | 428.5624 | 428.5624 | 348.5624 | 23.2375 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7.5353 | 4.4647 |  | 0 | 28 |  | 0 | 59.7604 | 0 | 19.7604 |  | 0 |  | -428.5624 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4647 | 4.7625 | 19.7604 | TOTAL DRILLING | 52 | days | 808 | hrs
2025-12-26 | Fri | Drilling | 16 | 16 | 392 | 960 | 440.883 | 440.883 | 360.883 | 24.0589 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 7.8559 | 4.1441 |  | 0 | 28 |  | 0 | 61.8138 | 2.0534 | 21.8138 |  | 20 |  | -440.883 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.1441 | 3.9411 | 21.8138 | TOTAL BAILING | 9 | days | 131 | hrs
2025-12-27 | Sat | Drilling | 16 | 16 | 408 | 960 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 8.1766 | 3.8234 |  | 0 | 28 |  | 0 | 63.8415 | 2.0277 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.8234 | 3.1301 | 3.8415
2025-12-28 | Sun | Drilling | 16 | 16 | 424 | 960 | 465.066 | 465.066 | 385.066 | 25.6711 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 8.4972 | 3.5028 |  | 0 | 28 |  | 0 | 65.8443 | 2.0028 | 5.8443 |  | 0 |  | -465.066 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.5028 | 2.3289 | 5.8443 | TOTAL WORKING | 79 | days | 1167 | hrs
2025-12-29 | Mon | Drilling | 16 | 16 | 440 | 960 | 476.9394 | 476.9394 | 396.9394 | 26.4626 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 8.8179 | 3.1821 |  | 0 | 28 |  | 0 | 67.8232 | 1.9789 | 7.8232 |  | 0 |  | -476.9394 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.1821 | 1.5374 | 7.8232 | TOTAL REST | 13 | days
2025-12-30 | Tue | Drilling | 16 | 16 | 456 | 960 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 9.1385 | 2.8615 |  | 0 | 28 |  | 0 | 69.779 | 1.9558 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.8615 | 0.75505 | 9.779
2025-12-31 | Wed | REST | 0 | 0 | 456 | 0 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9.1385 | 2.8615 |  | 0 | 28 |  | 6 | 69.779 | 0 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 2.8615 | 0.75505 | 9.779 | FIELD TIME | 92 | days
2026-01-01 | Thu | Drilling | 16 | 16 | 472 | 960 | 500.2752 | 500.2752 | 420.2752 | 28.0183 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 9.4592 | 2.5408 |  | 0 | 34 |  | 0 | 71.7125 | 1.9335 | 11.7125 |  | 0 |  | -500.2752 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.5408 | 5.9817 | 11.7125 | SLACK | -10 | days
2026-01-02 | Fri | Drilling | 16 | 16 | 488 | 960 | 511.7468 | 511.7468 | 431.7468 | 28.7831 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 9.7798 | 2.2202 |  | 0 | 34 |  | 0 | 73.6245 | 1.9119 | 13.6245 |  | 0 |  | -511.7468 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.2202 | 5.2169 | 13.6245
2026-01-03 | Sat | Drilling | 16 | 16 | 504 | 960 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 10.1005 | 1.8995 |  | 0 | 34 |  | 0 | 75.5156 | 1.8911 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8995 | 4.4604 | 15.5156
2026-01-04 | Sun | REST | 0 | 0 | 504 | 0 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 10.1005 | 1.8995 |  | 0 | 34 |  | 0 | 75.5156 | 0 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8995 | 4.4604 | 15.5156
2026-01-05 | Mon | Drilling | 16 | 16 | 520 | 960 | 534.3187 | 534.3187 | 454.3187 | 30.2879 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 10.4211 | 1.5789 |  | 0 | 34 |  | 0 | 77.3864 | 1.8709 | 17.3864 |  | 0 |  | -534.3187 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.5789 | 3.7121 | 17.3864
2026-01-06 | Tue | Drilling | 16 | 16 | 536 | 960 | 545.4267 | 545.4267 | 465.4267 | 31.0284 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 10.7418 | 1.2582 |  | 0 | 34 |  | 0 | 79.2378 | 1.8513 | 19.2378 |  | 0 |  | -545.4267 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.2582 | 2.9716 | 19.2378
2026-01-07 | Wed | Drilling | 16 | 16 | 552 | 960 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 11.0624 | 0.93756 |  | 0 | 34 |  | 0 | 81.0702 | 1.8324 | 21.0702 |  | 20 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 0.93756 | 2.2386 | 21.0702
2026-01-08 | Thu | Drilling | 16 | 16 | 568 | 960 | 567.3051 | 567.3051 | 487.3051 | 32.487 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 11.3831 | 0.61691 |  | 0 | 34 |  | 0 | 82.8842 | 1.814 | 2.8842 |  | 0 |  | -567.3051 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.61691 | 1.513 | 2.8842
2026-01-09 | Fri | Drilling | 16 | 16 | 584 | 960 | 578.0821 | 578.0821 | 498.0821 | 33.2055 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 11.7037 | 0.29626 |  | 6 | 34 |  | 0 | 84.6803 | 1.7962 | 4.6803 |  | 0 |  | -578.0821 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.29626 | 0.79453 | 4.6803
2026-01-10 | Sat | Drilling | 16 | 16 | 600 | 960 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.0244 | 5.9756 |  | 0 | 34 |  | 0 | 86.4592 | 1.7788 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.9756 | 0.082991 | 6.4592
2026-01-11 | Sun | REST | 0 | 0 | 600 | 0 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.0244 | 5.9756 |  | 0 | 34 |  | 6 | 86.4592 | 0 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.9756 | 0.082991 | 6.4592
2026-01-12 | Mon | Drilling | 16 | 16 | 616 | 960 | 599.3272 | 599.3272 | 519.3272 | 34.6218 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.345 | 5.655 |  | 0 | 40 |  | 0 | 88.2212 | 1.762 | 8.2212 |  | 0 |  | -599.3272 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.655 | 5.3782 | 8.2212
2026-01-13 | Tue | Drilling | 16 | 16 | 632 | 960 | 609.801 | 609.801 | 529.801 | 35.3201 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.6657 | 5.3343 |  | 0 | 40 |  | 0 | 89.9668 | 1.7456 | 9.9668 |  | 0 |  | -609.801 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3343 | 4.6799 | 9.9668
2026-01-14 | Wed | Drilling | 16 | 16 | 648 | 960 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 12.9863 | 5.0137 |  | 0 | 40 |  | 0 | 91.6966 | 1.7297 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 3.988 | 11.6966
2026-01-15 | Thu | Drilling | 16 | 16 | 664 | 960 | 630.4649 | 630.4649 | 550.4649 | 36.6977 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.307 | 4.693 |  | 0 | 40 |  | 0 | 93.4108 | 1.7142 | 13.4108 |  | 0 |  | -630.4649 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.693 | 3.3023 | 13.4108
2026-01-16 | Fri | Drilling | 16 | 16 | 680 | 960 | 640.6598 | 640.6598 | 560.6598 | 37.3773 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.6276 | 4.3724 |  | 0 | 40 |  | 0 | 95.11 | 1.6992 | 15.11 |  | 0 |  | -640.6598 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3724 | 2.6227 | 15.11
2026-01-17 | Sat | Drilling | 16 | 16 | 696 | 960 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 13.9483 | 4.0517 |  | 0 | 40 |  | 0 | 96.7944 | 1.6845 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 1.9489 | 16.7944
2026-01-18 | Sun | REST | 0 | 0 | 696 | 0 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13.9483 | 4.0517 |  | 0 | 40 |  | 0 | 96.7944 | 0 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 1.9489 | 16.7944
2026-01-19 | Mon | Drilling | 16 | 16 | 712 | 960 | 660.7876 | 660.7876 | 580.7876 | 38.7192 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.2689 | 3.7311 |  | 0 | 40 |  | 0 | 98.4646 | 1.6702 | 18.4646 |  | 0 |  | -660.7876 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.7311 | 1.2808 | 18.4646
2026-01-20 | Tue | Drilling | 16 | 16 | 728 | 960 | 670.7248 | 670.7248 | 590.7248 | 39.3817 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.5896 | 3.4104 |  | 0 | 40 |  | 6 | 100.1208 | 1.6562 | 20.1208 |  | 20 |  | -670.7248 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | -216 | 3.4104 | 0.61834 | 20.1208
2026-01-21 | Wed | Drilling | 16 | 16 | 744 | 960 | 680.5804 | 680.5804 | 600.5804 | 40.0387 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 14.9102 | 3.0898 |  | 0 | 46 |  | 0 | 101.7634 | 1.6426 | 1.7634 |  | 0 |  | -680.5804 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.0898 | 5.9613 | 1.7634
2026-01-22 | Thu | Drilling | 16 | 16 | 760 | 960 | 690.3562 | 690.3562 | 610.3562 | 40.6904 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.2309 | 2.7691 |  | 0 | 46 |  | 0 | 103.3927 | 1.6293 | 3.3927 |  | 0 |  | -690.3562 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.7691 | 5.3096 | 3.3927
2026-01-23 | Fri | Drilling | 16 | 16 | 776 | 960 | 700.0543 | 700.0543 | 620.0543 | 41.337 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.5515 | 2.4485 |  | 0 | 46 |  | 0 | 105.0091 | 1.6163 | 5.0091 |  | 0 |  | -700.0543 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.4485 | 4.663 | 5.0091
2026-01-24 | Sat | Drilling | 16 | 16 | 792 | 960 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.32065 | 15.8722 | 2.1278 |  | 0 | 46 |  | 0 | 106.6127 | 1.6037 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1278 | 4.0216 | 6.6127
2026-01-25 | Sun | REST | 0 | 0 | 792 | 0 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 15.8722 | 2.1278 |  | 0 | 46 |  | 0 | 106.6127 | 0 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1278 | 4.0216 | 6.6127
2026-01-26 | Mon | Drilling | 16 | 16 | 808 | 960 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0.32065 | 16.1928 | 1.8072 |  | 0 | 46 |  | 0 | 108.2041 | 1.5913 | 8.2041 |  | 0 |  | -719.2244 | -80 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8072 | 3.385 | 8.2041
2026-01-27 | Tue | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 16 | 960 | 198.3125 | 7.0988 | 7.0988 | 198.3125 | 0.39024 | 16.5831 | 1.4169 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -198.3125 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4169 | 10.4838 | 8.2041
2026-01-28 | Wed | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 32 | 960 | 311.7149 | 13.9029 | 6.8041 | 311.7149 | 0.39024 | 16.9733 | 1.0267 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -311.7149 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.0267 | 17.2879 | 8.2041
2026-01-29 | Thu | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 48 | 960 | 400.4713 | 19.2283 | 5.3254 | 400.4713 | 0.39024 | 17.3636 | 0.63642 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.63642 | 22.6133 | 8.2041
2026-01-30 | Fri | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 64 | 960 | 475.9111 | 23.7547 | 4.5264 | 475.9111 | 0.39024 | 17.7538 | 0.24618 |  | 6 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -475.9111 | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.24618 | 27.1397 | 8.2041
2026-01-31 | Sat | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 80 | 960 | 542.6755 | 27.7605 | 4.0059 | 542.6755 | 0.39024 | 18.1441 | 5.8559 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -542.6755 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.8559 | 31.1456 | 8.2041
2026-02-01 | Sun | REST | 0 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 80 | 0 | 542.6755 | 27.7605 | 0 | 542.6755 | 0 | 18.1441 | 5.8559 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -542.6755 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.8559 | 31.1456 | 8.2041
2026-02-02 | Mon | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 96 | 960 | 603.2085 | 31.3925 | 3.632 | 603.2085 | 0.39024 | 18.5343 | 5.4657 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.4657 | 34.7776 | 8.2041
2026-02-03 | Tue | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 112 | 960 | 658.985 | 34.7391 | 3.3466 | 658.985 | 0.39024 | 18.9246 | 5.0754 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -658.985 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0754 | 38.1241 | 8.2041
2026-02-04 | Wed | Bailing | 16 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 16 | 128 | 960 | 710.9762 | 37.8586 | 3.1195 | 710.9762 | 0.39024 | 19.3148 | 4.6852 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -710.9762 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.6852 | 41.2436 | 8.2041
2026-02-05 | Thu | Bailing | 3 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 3 | 131 | 180 | 720.3618 | 38.4217 | 0.56314 | 720.3618 | 0.073171 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 8.2041
2026-02-06 | Fri | Drill & Tent Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 8.2041
2026-02-07 | Sat | Drill & Tent Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 8.2041
2026-02-08 | Sun | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 8.2041
2026-02-09 | Mon | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 8.2041
2026-02-10 | Tue | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 8.2041
2026-02-11 | Wed | Camp Teardown | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 8.2041
2026-02-12 | Thu | Camp Closed | 12 | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 8.2041 |  | 8.2041 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.612 | 41.8067 | 8.2041
2026-02-13 | Fri |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-14 | Sat |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-15 | Sun |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-16 | Mon |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-17 | Tue |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-18 | Wed |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-19 | Thu |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-20 | Fri |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-21 | Sat |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-22 | Sun |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-23 | Mon |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-24 | Tue |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-25 | Wed |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-26 | Thu |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-27 | Fri |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-02-28 | Sat |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
2026-03-01 | Sun |  |  | 0 | 808 | 0 | 719.2244 | 719.2244 | 639.2244 | 42.615 | 0 | 131 | 0 | 720.3618 | 38.4217 | 0 | 720.3618 | 0 | 19.388 | 4.612 |  | 0 | 46 |  | 0 | 108.2041 | 0 | 0 |  | 0 |  | -719.2244 | -720.3618 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.612 | 41.8067 | 0
Formulas:
Date = [Date, row above]+1

## 08-07-25-Scen7-GennyFail
Date | Day | Drilling Critical Path | Working Day (hrs) | Drilling Day (hrs) | Cumulative Drilling Time (hrs) | Drilling Day (mins) | New Drilling Depth (m) | End of Day Drill Depth (m) | Drill Fluid Height (m) | Drill Fluid Used (Drums) | Bailing Day (hrs) | Cumulative Bailing Time (hrs) | Bailing Day (mins) | New Bailing Depth (m) | Cumulative Drill Fluid Recovered (Drums) | Daily Drill Fluid Recovered (Drums) | End of Day Bailing Depth (m) | Drilling/Bailing Fuel Burn (Drums) | Cumulative Drilling/Bailing Fuel Burn (Drums) | Drilling/Bailing Fuel in Field (Drums) | Drilling/Bailing Fuel Planned Arrival (Drums) | Fuel Still Required for Drilling/Bailing IN (Drums) | Drill Fluid in Field (Drums) | Drill Fluid Planned Arrival (Drums) | Drill Fluid Still Required IN (Drums) | Ice Core Boxes Filled | Today's Ice Core Boxes Filled | Filled Ice Core Boxes in Field | Ice Core Boxes Planned Removal | Ice Core Box Flight Ready OUT | Input | End of Day Drill Depth | End of Day Bailing Depth | Bedrock | 10,000YBP Min | 10,000YBP Max | Able to Output | Drilling Fuel Planned | Drilling Fuel Still Needed | Drill Fluid Planned In | Drill Fluid Still Needed In | Ice Core Boxes Planned OUT | Ice Core Boxes Still Needed OUT | Drilling Fuel in Camp | D60 in Camp (excl Borehole) | Filled Core Boxes in Camp | Scenario 7: Genny failure. Can we save the season if a spare is available in Rothera 01/12/2025? (best case genny in camp 03/12/2025). Yes, by working 24 hour shifts… | [6 empty] | How to use this Scenario Planner:
2025-11-12 | Wed | Open Camp | 12 | 0 | 0 | 0 | 0 |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 | 0 | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 |  | Date | PAX |  |  | Date | PAX | This is an input cell |  | input | do not change values in any cell but these
2025-11-13 | Thu | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | First Input | 2025-11-12 | 5 |  | First Output | 2026-01-21 | 5 | Do not cut and paste cells as it will break the formulae that make this sheet work (you can copy though)
2025-11-14 | Fri | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | Second Input | 2025-11-17 | 5 |  | Second Output | 2026-02-02 | 5
2025-11-15 | Sat | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 1. Set the input and output dates (found above the charts)
2025-11-16 | Sun | Dig Out | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 2. Set drill, project, and logistics constraints in the "Drilling Spec" sheet.
2025-11-17 | Mon | REST | 0 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [7 empty] | 3. Fill in the "Drilling Critical Path" and "Working Day (hrs)" columns with the activities that will be undertaken each day. There are special values you can put in "Drilling Critical Path" that will help - you must type them in without typos!
2025-11-18 | Tue | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-19 | Wed | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-20 | Thu | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | REST |  | counts as a rest day.
2025-11-21 | Fri | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Drilling |  | counts the hours towards drilling progress.
2025-11-22 | Sat | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Bailing |  | counts the hours towards bailing progress.
2025-11-23 | Sun | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Camp Closed |  | notes when we're finished in camp.
2025-11-24 | Mon | Drill & Tent Setup | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | The upper graph will show drilling and bailing progress given your inputted activities, ensure you reach target depth/bedrock!
2025-11-25 | Tue | REST | 0 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-26 | Wed | Waiting/Other Science | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Note: You need to consider yourself whether the inputted activities are realistic given the staffing available.
2025-11-27 | Thu | Waiting/Other Science | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-28 | Fri | Waiting/Other Science | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | The graph also will show crosses on the dates where logistic input is required to keep the planned schedule moving. For fuel and drilling fluid, crosses mark the last chance to get more in before drilling ops shut down. For ice core boxes crosses mark the earliest a full load of boxes would be ready for removal.
2025-11-29 | Sat | Waiting/Other Science | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-11-30 | Sun | Waiting/Other Science | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-12-01 | Mon | Waiting/Other Science | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-12-02 | Tue | Waiting/Other Science | 12 | 0 | 0 | 0 | #VALUE! |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 |  | 0 | #VALUE! | 0 | 0 |  | 0 |  | #N/A | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0
2025-12-03 | Wed | Genny Setup | 12 | 0 | 0 | 0 | #VALUE! | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 4 |  | 0 | 0 | 0 | 0 |  | 0 |  | -70 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0 | 4 | 0 | [8 empty] | Note: Drilling/Bailing fuel only counts what is needed for drilling ops, fuel for other camp activities should be considered separately.
2025-12-04 | Thu | Drilling | 8 | 8 | 8 | 480 | 79.8333 | 79.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.16033 | 5.8397 |  | 0 | 4 |  | 0 | 1.6389 | 1.6389 | 1.6389 |  | 0 |  | -79.8333 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.8397 | 4 | 1.6389
2025-12-05 | Fri | Drilling | 8 | 8 | 16 | 480 | 89.5102 | 89.5102 | 9.5102 | 0.63401 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.32065 | 5.6793 |  | 0 | 4 |  | 0 | 3.2517 | 1.6128 | 3.2517 |  | 0 |  | -89.5102 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6793 | 3.366 | 3.2517 | [7 empty] | 4. Schedule deliveries of fuel and drill fluid, and pickup of ice core boxes. Use the "Drilling/Bailing Fuel Planned Arrival (Drums)", " Drill Fluid Planned Arrival (Drums)", and "Ice Core Boxes Planned Removal" columns for this. These will be marked on the graph as circles, and the cross showing needs that remain unscheduled will update automatically.
2025-12-06 | Sat | Drilling | 8 | 8 | 24 | 480 | 99.0379 | 99.0379 | 19.0379 | 1.2692 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16033 | 0.48098 | 5.519 |  | 0 | 4 |  | 0 | 4.8397 | 1.5879 | 4.8397 |  | 0 |  | -99.0379 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.519 | 2.7308 | 4.8397
2025-12-07 | Sun | Drilling | 24 | 24 | 48 | 1440 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 0.96195 | 5.038 |  | 0 | 4 |  | 0 | 9.4651 | 4.6254 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.038 | 0.88064 | 9.4651
2025-12-08 | Mon | REST | 0 | 0 | 48 | 0 | 126.7904 | 126.7904 | 46.7904 | 3.1194 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.96195 | 5.038 |  | 0 | 4 |  | 6 | 9.4651 | 0 | 9.4651 |  | 0 |  | -126.7904 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.038 | 0.88064 | 9.4651
2025-12-09 | Tue | Drilling | 24 | 24 | 72 | 1440 | 153.4144 | 153.4144 | 73.4144 | 4.8943 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.4429 | 4.5571 |  | 0 | 10 |  | 0 | 13.9024 | 4.4373 | 13.9024 |  | 0 |  | -153.4144 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5571 | 5.1057 | 13.9024
2025-12-10 | Wed | Drilling | 24 | 24 | 96 | 1440 | 179.0374 | 179.0374 | 99.0374 | 6.6025 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 1.9239 | 4.0761 |  | 0 | 10 |  | 0 | 18.1729 | 4.2705 | 18.1729 |  | 0 |  | -179.0374 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0761 | 3.3975 | 18.1729 | [8 empty] | The totals of these 'consumables' in camp are shown in the lower graph. (Note drilling fluid in the borehole is excluded).
2025-12-11 | Thu | Drilling | 24 | 24 | 120 | 1440 | 203.7644 | 203.7644 | 123.7644 | 8.251 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.4049 | 3.5951 |  | 0 | 10 |  | 0 | 22.2941 | 4.1212 | 22.2941 |  | 20 |  | -203.7644 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 3.5951 | 1.749 | 22.2941
2025-12-12 | Fri | Drilling | 24 | 24 | 144 | 1440 | 227.6833 | 227.6833 | 147.6833 | 9.8456 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 2.8859 | 3.1141 |  | 0 | 10 |  | 6 | 26.2805 | 3.9865 | 6.2805 |  | 0 |  | -227.6833 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 3.1141 | 0.15445 | 6.2805 | [8 empty] | Note: Check the "Filled Ice Core Boxes in Field" column to avoid scheduling removing more core boxes than you have ready!
2025-12-13 | Sat | Drilling | 24 | 24 | 168 | 1440 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.3668 | 2.6332 |  | 0 | 16 |  | 0 | 30.1447 | 3.8642 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.6332 | 4.6088 | 10.1447
2025-12-14 | Sun | REST | 0 | 0 | 168 | 0 | 250.8684 | 250.8684 | 170.8684 | 11.3912 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.3668 | 2.6332 |  | 0 | 16 |  | 0 | 30.1447 | 0 | 10.1447 |  | 0 |  | -250.8684 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.6332 | 4.6088 | 10.1447 | [7 empty] | 5. Assess feasibility of the planned season (logistic demands realistic, enough PAX in field, enough time for issues and bad weather, rest periods in long seasons, room for other non-drilling activities, etc)
2025-12-15 | Mon | Drilling | 24 | 24 | 192 | 1440 | 273.3836 | 273.3836 | 193.3836 | 12.8922 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 3.8478 | 2.1522 |  | 0 | 16 |  | 0 | 33.8973 | 3.7525 | 13.8973 |  | 0 |  | -273.3836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1522 | 3.1078 | 13.8973
2025-12-16 | Tue | Drilling | 24 | 24 | 216 | 1440 | 295.2836 | 295.2836 | 215.2836 | 14.3522 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.3288 | 1.6712 |  | 0 | 16 |  | 0 | 37.5473 | 3.65 | 17.5473 |  | 0 |  | -295.2836 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6712 | 1.6478 | 17.5473
2025-12-17 | Wed | Drilling | 24 | 24 | 240 | 1440 | 316.6164 | 316.6164 | 236.6164 | 15.7744 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 4.8098 | 1.1902 |  | 0 | 16 |  | 6 | 41.1027 | 3.5555 | 21.1027 |  | 20 |  | -316.6164 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | -216 | 1.1902 | 0.22557 | 21.1027 | [7 empty] | 6. Assess getting everything out again after! There'll be a lot of recovered drill fluid in drums…
2025-12-18 | Thu | Drilling | 24 | 24 | 264 | 1440 | 337.4238 | 337.4238 | 257.4238 | 17.1616 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.2907 | 0.70927 |  | 0 | 22 |  | 0 | 44.5706 | 3.4679 | 4.5706 |  | 0 |  | -337.4238 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.70927 | 4.8384 | 4.5706
2025-12-19 | Fri | Drilling | 24 | 24 | 288 | 1440 | 357.7428 | 357.7428 | 277.7428 | 18.5162 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 5.7717 | 0.22829 |  | 6 | 22 |  | 0 | 47.9571 | 3.3865 | 7.9571 |  | 0 |  | -357.7428 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.22829 | 3.4838 | 7.9571
2025-12-20 | Sat | Drilling | 24 | 24 | 312 | 1440 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.2527 | 5.7473 |  | 0 | 22 |  | 0 | 51.2677 | 3.3106 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7473 | 2.1596 | 11.2677
2025-12-21 | Sun | REST | 0 | 0 | 312 | 0 | 377.6063 | 377.6063 | 297.6063 | 19.8404 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.2527 | 5.7473 |  | 0 | 22 |  | 0 | 51.2677 | 0 | 11.2677 |  | 0 |  | -377.6063 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.7473 | 2.1596 | 11.2677
2025-12-22 | Mon | Drilling | 24 | 24 | 336 | 1440 | 397.0436 | 397.0436 | 317.0436 | 21.1362 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 6.7337 | 5.2663 |  | 0 | 22 |  | 6 | 54.5073 | 3.2396 | 14.5073 |  | 0 |  | -397.0436 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.2663 | 0.86376 | 14.5073
2025-12-23 | Tue | Drilling | 24 | 24 | 360 | 1440 | 416.0811 | 416.0811 | 336.0811 | 22.4054 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.2146 | 4.7854 |  | 0 | 28 |  | 0 | 57.6802 | 3.1729 | 17.6802 |  | 0 |  | -416.0811 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.7854 | 5.5946 | 17.6802
2025-12-24 | Wed | Drilling | 24 | 24 | 384 | 1440 | 434.7424 | 434.7424 | 354.7424 | 23.6495 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 7.6956 | 4.3044 |  | 0 | 28 |  | 0 | 60.7904 | 3.1102 | 20.7904 |  | 20 |  | -434.7424 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.3044 | 4.3505 | 20.7904
2025-12-25 | Thu | REST | 24 | 0 | 384 | 0 | 434.7424 | 434.7424 | 354.7424 | 23.6495 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7.6956 | 4.3044 |  | 0 | 28 |  | 0 | 60.7904 | 2.1316e-14 | 0.79039 |  | 0 |  | -434.7424 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3044 | 4.3505 | 0.79039 | TOTAL DRILLING | 36 | days | 816 | hrs
2025-12-26 | Fri | Drilling | 24 | 24 | 408 | 1440 | 453.0489 | 453.0489 | 373.0489 | 24.8699 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.1766 | 3.8234 |  | 0 | 28 |  | 0 | 63.8415 | 3.0511 | 3.8415 |  | 0 |  | -453.0489 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.8234 | 3.1301 | 3.8415 | TOTAL BAILING | 6 | days | 132 | hrs
2025-12-27 | Sat | Drilling | 24 | 24 | 432 | 1440 | 471.0203 | 471.0203 | 391.0203 | 26.068 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 8.6576 | 3.3424 |  | 0 | 28 |  | 0 | 66.8367 | 2.9952 | 6.8367 |  | 0 |  | -471.0203 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3424 | 1.932 | 6.8367
2025-12-28 | Sun | Drilling | 24 | 24 | 456 | 1440 | 488.6742 | 488.6742 | 408.6742 | 27.2449 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.1385 | 2.8615 |  | 0 | 28 |  | 6 | 69.779 | 2.9423 | 9.779 |  | 0 |  | -488.6742 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 2.8615 | 0.75505 | 9.779 | TOTAL WORKING | 68 | days | 1296 | hrs
2025-12-29 | Mon | Drilling | 24 | 24 | 480 | 1440 | 506.0269 | 506.0269 | 426.0269 | 28.4018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 9.6195 | 2.3805 |  | 0 | 34 |  | 0 | 72.6712 | 2.8921 | 12.6712 |  | 0 |  | -506.0269 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3805 | 5.5982 | 12.6712 | TOTAL REST | 11 | days
2025-12-30 | Tue | Drilling | 24 | 24 | 504 | 1440 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.1005 | 1.8995 |  | 0 | 34 |  | 0 | 75.5156 | 2.8444 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8995 | 4.4604 | 15.5156
2025-12-31 | Wed | REST | 0 | 0 | 504 | 0 | 523.0933 | 523.0933 | 443.0933 | 29.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 10.1005 | 1.8995 |  | 0 | 34 |  | 0 | 75.5156 | 1.4211e-14 | 15.5156 |  | 0 |  | -523.0933 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.8995 | 4.4604 | 15.5156 | FIELD TIME | 79 | days
2026-01-01 | Thu | Drilling | 24 | 24 | 528 | 1440 | 539.8871 | 539.8871 | 459.8871 | 30.6591 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 10.5815 | 1.4185 |  | 0 | 34 |  | 0 | 78.3145 | 2.799 | 18.3145 |  | 0 |  | -539.8871 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4185 | 3.3409 | 18.3145 | SLACK | 3 | days
2026-01-02 | Fri | Drilling | 24 | 24 | 552 | 1440 | 556.4211 | 556.4211 | 476.4211 | 31.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.0624 | 0.93756 |  | 0 | 34 |  | 0 | 81.0702 | 2.7557 | 21.0702 |  | 20 |  | -556.4211 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 0.93756 | 2.2386 | 21.0702
2026-01-03 | Sat | Drilling | 24 | 24 | 576 | 1440 | 572.7068 | 572.7068 | 492.7068 | 32.8471 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 11.5434 | 0.45659 |  | 6 | 34 |  | 0 | 83.7845 | 2.7143 | 3.7845 |  | 0 |  | -572.7068 | #N/A | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.45659 | 1.1529 | 3.7845
2026-01-04 | Sun | Drilling | 24 | 24 | 600 | 1440 | 588.7551 | 588.7551 | 508.7551 | 33.917 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.0244 | 5.9756 |  | 0 | 34 |  | 6 | 86.4592 | 2.6747 | 6.4592 |  | 0 |  | -588.7551 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 5.9756 | 0.082991 | 6.4592
2026-01-05 | Mon | Drilling | 24 | 24 | 624 | 1440 | 604.5762 | 604.5762 | 524.5762 | 34.9717 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.5054 | 5.4946 |  | 0 | 40 |  | 0 | 89.096 | 2.6368 | 9.096 |  | 0 |  | -604.5762 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.4946 | 5.0283 | 9.096
2026-01-06 | Tue | Drilling | 24 | 24 | 648 | 1440 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 12.9863 | 5.0137 |  | 0 | 40 |  | 0 | 91.6966 | 2.6005 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 3.988 | 11.6966
2026-01-07 | Wed | REST | 0 | 0 | 648 | 0 | 620.1794 | 620.1794 | 540.1794 | 36.012 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.9863 | 5.0137 |  | 0 | 40 |  | 0 | 91.6966 | 0 | 11.6966 |  | 0 |  | -620.1794 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.0137 | 3.988 | 11.6966
2026-01-08 | Thu | Drilling | 24 | 24 | 672 | 1440 | 635.5735 | 635.5735 | 555.5735 | 37.0382 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 13.4673 | 4.5327 |  | 0 | 40 |  | 0 | 94.2623 | 2.5657 | 14.2623 |  | 0 |  | -635.5735 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5327 | 2.9618 | 14.2623
2026-01-09 | Fri | Drilling | 24 | 24 | 696 | 1440 | 650.7667 | 650.7667 | 570.7667 | 38.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 13.9483 | 4.0517 |  | 0 | 40 |  | 0 | 96.7944 | 2.5322 | 16.7944 |  | 0 |  | -650.7667 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.0517 | 1.9489 | 16.7944
2026-01-10 | Sat | Drilling | 24 | 24 | 720 | 1440 | 665.7666 | 665.7666 | 585.7666 | 39.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 14.4293 | 3.5707 |  | 0 | 40 |  | 0 | 99.2944 | 2.5 | 19.2944 |  | 0 |  | -665.7666 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.5707 | 0.9489 | 19.2944
2026-01-11 | Sun | REST | 0 | 0 | 720 | 0 | 665.7666 | 665.7666 | 585.7666 | 39.0511 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 14.4293 | 3.5707 |  | 0 | 40 |  | 6 | 99.2944 | 0 | 19.2944 |  | 0 |  | -665.7666 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | -144 | #N/A | #N/A | 3.5707 | 0.9489 | 19.2944
2026-01-12 | Mon | Drilling | 24 | 24 | 744 | 1440 | 680.5804 | 680.5804 | 600.5804 | 40.0387 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 14.9102 | 3.0898 |  | 0 | 46 |  | 0 | 101.7634 | 2.469 | 21.7634 |  | 20 |  | -680.5804 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 3.0898 | 5.9613 | 21.7634
2026-01-13 | Tue | Drilling | 24 | 24 | 768 | 1440 | 695.2149 | 695.2149 | 615.2149 | 41.0143 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 15.3912 | 2.6088 |  | 0 | 46 |  | 0 | 104.2025 | 2.4391 | 4.2025 |  | 0 |  | -695.2149 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.6088 | 4.9857 | 4.2025
2026-01-14 | Wed | Drilling | 24 | 24 | 792 | 1440 | 709.6765 | 709.6765 | 629.6765 | 41.9784 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.48098 | 15.8722 | 2.1278 |  | 0 | 46 |  | 0 | 106.6127 | 2.4103 | 6.6127 |  | 0 |  | -709.6765 | #N/A | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.1278 | 4.0216 | 6.6127
2026-01-15 | Thu | Drilling | 24 | 24 | 816 | 1440 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0.48098 | 16.3532 | 1.6468 |  | 0 | 46 |  | 0 | 108.9952 | 2.3824 | 8.9952 |  | 0 |  | -723.9711 | -80 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6468 | 3.0686 | 8.9952
2026-01-16 | Fri | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 24 | 1440 | 259.4033 | 10.7642 | 10.7642 | 259.4033 | 0.58537 | 16.9385 | 1.0615 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -259.4033 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.0615 | 13.8328 | 8.9952
2026-01-17 | Sat | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 48 | 1440 | 400.4713 | 19.2283 | 8.4641 | 400.4713 | 0.58537 | 17.5239 | 0.4761 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.4761 | 22.2969 | 8.9952
2026-01-18 | Sun | REST | 0 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 48 | 0 | 400.4713 | 19.2283 | 0 | 400.4713 | 0 | 17.5239 | 0.4761 |  | 6 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -400.4713 | -720 | -624 | -688 | #N/A | #N/A | -72 | #N/A | #N/A | #N/A | #N/A | 0.4761 | 22.2969 | 8.9952
2026-01-19 | Mon | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 72 | 1440 | 510.1938 | 25.8116 | 6.5834 | 510.1938 | 0.58537 | 18.1093 | 5.8907 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -510.1938 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.8907 | 28.8802 | 8.9952
2026-01-20 | Tue | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 96 | 1440 | 603.2085 | 31.3925 | 5.5809 | 603.2085 | 0.58537 | 18.6946 | 5.3054 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -603.2085 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3054 | 34.4611 | 8.9952
2026-01-21 | Wed | Bailing | 24 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 24 | 120 | 1440 | 685.4061 | 36.3244 | 4.9319 | 685.4061 | 0.58537 | 19.28 | 4.72 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -685.4061 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.72 | 39.393 | 8.9952
2026-01-22 | Thu | REST | 0 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 120 | 0 | 685.4061 | 36.3244 | 0 | 685.4061 | 0 | 19.28 | 4.72 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -685.4061 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.72 | 39.393 | 8.9952
2026-01-23 | Fri | Bailing | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 12 | 132 | 720 | 723.4668 | 38.608 | 2.2836 | 723.4668 | 0.29268 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 8.9952
2026-01-24 | Sat | Drill & Tent Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 8.9952
2026-01-25 | Sun | Drill & Tent Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 8.9952
2026-01-26 | Mon | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 8.9952
2026-01-27 | Tue | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 8.9952
2026-01-28 | Wed | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 8.9952
2026-01-29 | Thu | Camp Teardown | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 8.9952
2026-01-30 | Fri | Camp Closed | 12 | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 8.9952 |  | 8.9952 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | -216 | 4.4273 | 41.6766 | 8.9952
2026-01-31 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-01 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-02 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-03 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-04 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-05 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-06 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-07 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-08 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-09 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-10 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-11 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-12 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-13 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-14 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-15 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-16 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-17 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-18 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-19 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-20 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-21 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-22 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-23 | Mon |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-24 | Tue |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-25 | Wed |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-26 | Thu |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-27 | Fri |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-02-28 | Sat |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
2026-03-01 | Sun |  |  | 0 | 816 | 0 | 723.9711 | 723.9711 | 643.9711 | 42.9314 | 0 | 132 | 0 | 723.4668 | 38.608 | 0 | 723.4668 | 0 | 19.5727 | 4.4273 |  | 0 | 46 |  | 0 | 108.9952 | 0 | 0 |  | 0 |  | -723.9711 | -723.4668 | -720 | -624 | -688 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.4273 | 41.6766 | 0
Formulas:
Date = [Date, row above]+1

## Drilling Spec
Drill Spec | [5 empty] | Drilling Progress is Calculated as Below
Drop Length | l | 1.15 | m | 1.15 is average from Skytrain |  | Time to drill from 0m to dm; Td = d^2/lW + d/v + ds/l
Winch Speed | W | 43 | m/min | Skytrain |  | Therefore time to drill from d1 to d2; T = (d2^2-d1^2)/lW + (d2-d1)/v + (d2-d1)s/l
Drilling Speed | v | 0.12 | m/min | Skytrain |  | Therefore, given T and d1:
Surface Time per Run | s | 15 | min | est
Slack | e | 100% |  | 100% Slack makes drilling theory match Skytrain performance |  | d2 = (- sqrt(4d1^2v^2 + 4d1vW(l+sv) + W(l^2W + 2lv(sW +2vT) +s^2v^2W)) + lW + svW) / 2v
AND
Bailing Spec | [5 empty] | d2 = (+ sqrt(4d1^2v^2 + 4d1vW(l+sv) + W(l^2W + 2lv(sW +2vT) +s^2v^2W)) - lW - svW) / 2v
Drop Length | lB | 3 | m | 1.5m for bailer, 3m for bunged outer barrel
Winch Speed | WB | 43 | m/min | Skytrain |  | To account for Slack, which makes this maths line up with data from Skytrain, replace T with T/(1+e)
Bailing Speed | vB | 43 | m/min | No different from winching |  | Therefore,
Surface Time per Run | sB | 5 | min | est
Slack | eB | 50% |  | 50% Slack makes bailing theory match Skytrain performance |  | d2 = (- sqrt(4d1^2v^2 + 4d1vW(l+sv) + W(l^2W + 2lv(sW +2vT/(1+e)) +s^2v^2W)) + lW + svW) / 2v
AND
Fuel Requirements | [5 empty] | d2 = (+ sqrt(4d1^2v^2 + 4d1vW(l+sv) + W(l^2W + 2lv(sW +2vT/(1+e)) +s^2v^2W)) - lW - svW) / 2v
Winch Motor Fuel Use |  | 5 | L/hr | 9kW | EP18000TE fuel use from Cambridge testing
Drill Motor Fuel Use |  | 2.5 | L/hr | 0.6kW |  | With real world data, it seems the former always gives the negative result (with fixed, l,W,v,s,e), and the later the same result but positive. (Symmetrical about T=0). So we'll only use the positive result
Idling Fuel Use |  | 2.15 | L/hr
Winching Time per Run |  | 40 | min/run | guess as to average |  | d2 = (+ sqrt(4d1^2v^2 + 4d1vW(l+sv) + W(l^2W + 2lv(sW +2vT/(1+e)) +s^2v^2W)) - lW - svW) / 2v
Drilling Time per Run |  | 10 | min/run | guess as to average
Idling Time per Run |  | 10 | min/run | guess as to average
Drilling Fuel Consumption |  | 0.020041 | drum/hr | 205L drum
Bailing Fuel Consumption |  | 0.02439 | drum/hr | 205L drum
Project Info
Drilling Start Depth |  | 70 | m | REWIND
10,000BP Depth Min |  | 624 | m | REWIND
10,000BP Depth Max |  | 688 | m | REWIND
Bedrock Depth |  | 720 | m | REWIND
Drill Fluid Head Depth |  | 80 | m | REWIND
Drill Fluid Depth/Drum |  | 15 | m/drum | Deep Drill
Drill Fluid Recovery Rate |  | 90% |  | guess
Logistics Constraints
Petrol per Delivery |  | 6 | drums/flight | guess
Drill Fluid per Delivery |  | 6 | drums/flight | guess
Drill Fluid Already in Field |  | 4 | drums | guess
Core per Core Box |  | 6 | m/box | BE-OIC boxes take six 1m cores
Core Boxes per Flight |  | 20 | box/flight | guess
Constants used in drilling calculation
4vW(l+sv) | = | 60.888 | m^3/min^2
l^2W | = | 56.8675 | m/min
s^2v^2W | = | 139.32 | m^3/min
lW + svW | = | 126.85 | min^-1
Constants used in bailing calculation
4vBWB(lB+sBvB) | = | 1612328 | m^3/min^2
lB^2WB | = | 387 | m/min
sB^2vB^2WB | = | 1987675 | m^3/min
lBWB + sBvBWB | = | 9374 | min^-1